## Variation Account (hidden)
| Description | Variation Amount | Provision In Main BOQ | Difference
1 | Atm Works | 87456.5621 | 0
2 | Aircon | 58696.29 | #REF! | #REF!
3 | Raised Floor | 196867.66 |  | #N/A
4 | Server Room | 8990 |  | #N/A
5 | Electrical Cable Tray (Provisional) | 45000 |  | #N/A
6 | Transparent Burglar Bars | 96000 |  | #N/A
7 | Contingency | 49301.0512 | 100000 | #N/A
#N/A
| Total | 542311.5633 | #REF! | #REF!

## Raised Floor (hidden)
S/N | DESCRPTION OF WORKS | UNIT | QTY | RATE | AMOUNT
1 | Supply & install raised floor in Global Markets using ultra steel frames & 600 x 600 x 40mm thick panels | m2 | 55 | 2950 | 162250
2 | Preliminaries and general items | item | 1 |  | 7463.5 | 7463.5
| Sub total Cost Zmw |  |  |  | 169713.5
| Add 16% VAT |  |  |  | 27154.16
| Grand total Cost Zmw |  |  |  | 196867.66
Note on H6: Malambo Gumbo Ziko: P&G Rate is 4.6%=7463.5

## ATM (hidden)
S/N | DESCRPTION OF WORKS | UNIT | QTY | RATE | AMOUNT
1 | Construction of 150mm thick hollow conrete block wall | m2 | 28 | 135 | 3780
2 | 12mm thick plaster on both sides of 150mm thick wall | m2 | 56 | 35 | 1960
3 | Brickforce 150mm every third course | m | 48 | 10 | 480
4 | Supply & install alumimium partition marked Panel 1 size 6255w x 2800h glazed with 6,38mm clear laminated glass. | no | 1 | 23436 | 23436
5 | Supply & install alumimium partition marked Panel 2 size 2350w x 2800h glazed with 6,38mm clear laminated glass. | no | 1 | 8880 | 8880
6 | Supply & install steel door frame 900w x 2000h complete with Hardwood door & lock. | no | 1 | 4550 | 4550
7 | Supply & install retractable trellidor door size 900 x 2000h | no | 1 | 5500 | 5500
8 | Supply & install steel mesh with Y12 mild steel bars in ceiling vold | m2 | 13 | 439 | 5707
9 | Supply & install suspended ceiling in ATM Room | m2 | 13 | 205 | 2665
10 | Electrical works in ATM room, wiring, switch, socket, lighting. | item | 1 | 5000 | 5000
11 | Painting works of walls to ATM using Dulux paint | m2 | 56 | 45 | 2520
12 | Supply & Install skirting along new walls | m | 20 | 65 | 1300
13 | Provisional sum for making good floor tiles | m2 | 28 | 225 | 6300 | 72078 | 3315.588
14 | Preliminaries and General items | item | 1 |  | 3315.588
| Sub total Cost Zmw |  |  |  | 75393.588
| Add 16% VAT |  |  |  | 12062.9741
| Grand total Cost Zmw |  |  |  | 87456.5621
Note on C18: Malambo Gumbo Ziko: Y16 Bars not Y12
Note on H30: Malambo Gumbo Ziko: P&G Rate is 4.6%=3315.59

## Aircons (hidden)
S/N | DESCRPTION OF WORKS | UNIT | QTY | RATE | AMOUNT
1 | Carefully remove existing airconditioning cassatte units & reinstall to new position & make good all disturbed areas. | no | 7 | 1650 | 11550
2 | Carefully remove existing airconditioning cassatte units & reinstall to new position & make good all disturbed areas. | no | 8 | 1650 | 13200
3 | Re fill repositioned all airconditions with gas & fix new piping & armaflex & power cables | no | 7 | 3375 | 23625
4 | Supply & install ceramic floor tiles in kitchens on ground & first floor | m2 | 30 | 360 |  | 48375
2225.25
5 | Preliminaries and general items | item | 1 |  | 2225.25
| Sub total Cost Zmw |  |  |  | 50600.25
| Add 16% VAT |  |  |  | 8096.04
| Grand total Cost Zmw |  |  |  | 58696.29
Note on H10: Malambo Gumbo Ziko: Covered under Provisional Sum in BOQ
Note on H12: Malambo Gumbo Ziko: P&G Rate is 4.6%=2722.5

## UnPriced BoQ
PROPOSED REFURBISHMENT WORKS FOR ZANACO BRANCH- MUKUBA MALL
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
i) The agreement is to be the Standard Form of Building Contract Private Edition WITH QUANTITIES 1970 Edition (Revised 1972)
ii) Tenders are referred to the abovementioned documents for the full intent and meaning of each clause thereof (hereinafter referred to by heading and clause number only) for which such allowance must be made as may be considered necessary
iii) Tenders are strongly advised to price each Item in the Preliminaries Bill. Any item not priced will be assumed that its cost has been included elsewhere in the tender documents
iv) Where standard clauses or alternatives are not entirely applicable to this contract such modifications, corrections or supplements as will apply are given under each relevant clause heading
v ) Where any item is not relevant to this specific contract such item is marked N/A (signifying "not applicable")
| Carried to Collection |  |  | K
Page 1/1
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
SECTION "A" CONDITIONS OF CONTRACT
The Contractor shall refer to the conditions herein before mentioned for the intent and meaning of the clause 1 to 35 hereafter and allow whatever costs he may consider necessary against each clause together with Sub-Clauses in amplification of name.
A | Contractor's Obligations Clause No.1 |  | Item
B | Architect's Instruction Clause No.2 |  | Item
C | Contract Documents Clause No.3 |  | Item
(i) A list of the Drawings from which the contract Bills have been prepared is appended
(ii) Contractors may examine all the Drawings (Which may be seen at the office of the Architect during the normal office hours) and satisfy themselves regarding all details as no claim by reasons of ignorance in this connection will be entertained.
(iii) The Contractor shall satisfy himself as to the correctness of all Drawings and measurements; If the contractor finds any discrepancy in the Drawings or between the Drawings and the Bills of Quantities, he shall immediately refer the same to the Architect who will decide which one shall be followed
| (iv) Figured dimensions will be used in preference to scales mentioned on or attached to any Drawing |  | Item
D | Statutory Obligations, Notices, Fees and Charges clause No.4
| The contractor shall give all notices and descriptions required by any Ordinance or by any Regurations or By-Laws to the Local and other Authority in connection with the works, and is to deposit plans and obtain licences or permits as necessary and pay all fees legally demandable and keep the Employer indemnified at all times against any charges in this regard |  | Item
| Carried to Collection |  |  | K
Page 1/2
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Levels and Setting Out of the Works clause No.5
(i) All particulars and measurements for the general setting out of the works shall be taken upon the site in conjuction with the Drawings.
(ii) The Contractor shall acurately perform all setting out by a method to be approved by the Architect and provide all instruments, templets, rods and setting out boards, as may be necessary for this purpose and where required maintain these for reference during the progress of the works.
(iii) The contractor shall set the works in accordance with the Drawings and/or other instructions, from beacons, pegs, benchmarks or other fixed marks as may be shown on the drawings or otherwise indicated to him.
(iv) The Contractor shall be held responsible for the correct setting out of the works not only in regard to correct levels, depths, heights, slopes, gradients and any other dimensional characteristics of the works.
| (v) In all cases of doubt the contractor shall apply for specific instructions and shall obtain approval for the alignment of building works, floor levels, gradients and depths of drain and water supply before proceeding with further construction works |  | Item
| Carried to Collection |  |  | K
Page 1/3
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
Materials, Goods and Workmanship to Conform to Descriptions, Testing and Inspection
A | Clause No.6
(i) The materials, goods and workmanship are to be in accordance with the `Specifications of materials and workmanship'.
(ii) The Architect may, whenever he/she considers it desirable, test any materials before they leave the manufaturer's premises as well as after delivary on the site, and the Architect shall be at liberty to reject any material after delivery should he consider them unsatisfactory, notwithstanding the preliminary test and approval of the materials at the manufacturer's premises. The costs of these tests are to be borne by the contractor.
(iii) When directed by the Architect samples of materials (the sample being taken by the approved sampling methods) are to be supplied by the contractor for Laboratory tests and shall be delivered to the Laboratory by the contractor at his/her costs.
(iv) The contractor shall, whenever so instructed by the Architect, cutout sections of work executed or samples of materials incorporated therein and shall deliver them where directed for the purpose of testing. All work disturbed shall be made good forthwith by the contractor. All costs incurred in cutting out, making good and delivering as are foresaid, shall be borne by the contractor unless the results of the tests show that the material etc are in accordance with the contract.
| (v) The contractor shall furnish at his own cost any samples of materials or workmanship or any tests that may be called for by the Architects for approval or rejection and for any further samples or tests in the case of reflection until they are approved by the Architect unless otherwise provided for herein. |  | Item
| Carried to Collection |  |  | K
Page 1/4
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Foreman-In-ChargeClause No.8
(i) The Contractor shall provide full and adequate supervision during the progress of the works and shall keep a competent and authorized Agent or General foreman, approved by the Architect and shall give his whole time to the supervision of the works and must be able to speak, understand and write English and to receive and act upon (on behalf of the contractor) all instructions, directions or orders issued by the Architect or his representative.
| (ii) The Contractor shall provide, erect, maintain and remove on completion a suitable lock-up and weatherproof office on the site for the use of the Agent or General Foreman complete with all necessary fittings, furniture, lighting and attendance and for making this office available to the use of the Architect and Quantity Surveyor or their representative when visiting the site.In addition the contractor shall provide a drawing board and T-square and keep one complete set of drawing, specifications and bills of quantities or other document forming part of the contract on site at all times for the use of the Architect and Quantity Surveyor or their representatives. The position on which the office is to be erected must be agreed upon with the Architect beforehand. |  | Item
B | Clerk of Works Clause No.10
| When a Clerk of Works is appointed the Contractor shall provide for his use and the custody, instruments, drawings etc, an adequate and well lighted and ventilated lock-up temporary weather proof office with boarded or concrete floor, block wall and ceilings, desk, lock-up drawers of the appropriate size, stool, large drawing board and T-square, including providing adequate clearning and attendance required. The contractor shall allow for removing all at completion of the works |  | Item
C | Variations Provisional and Prime Cost Sums clause No.11
| Prime Cost Sums, Provisional Sums and Provisional Quantities are to be expended in whole or in part or omitted entirely from the Contract as directed in writing by the Architect. Any profit which may have been inserted by the Contractor against any P.C or Provisional Sum is to be treated as a percentage thereof and adjusted pro- rata thereto in the settlement of the Final Account. The period of Final Measurement is to be within 9 months from practical completion of the works |  | Item
| Carried to Collection |  |  | K
Page 1/5
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
Contract Bills
(i) The Bills of Quantities shall be priced in ink.
(ii) Any unauthorised alterations or qualifications made to the text of the Bills of Quantities may cause the tender to be disqualified and will in any case be ignored.
(iii) All items of measured work shall be priced in detail and tenders containing lump sums to cover trades or groups of work must be broken down to show the price of each item before they will be accepted. Lump sums to cover several items of preliminaries likewise shall be broken down if so required.
(iv) The rates put down by the Contractor against each item in these Contract Documents shall unless otherwise expressly provided to the contrary, or unless there is a separate item for extra labour,cutting and waste,shall be held to include for waste on materials, carriage carrying in and return of empties, hoisting,setting, fitting and fixing in position,making good and all other labours and anything else necessary for the proper completion of each item and for the establishment charges and profit.
(v) The Contractor shall be deemed to have made allowance in his prices generally to cover item of preliminaries,expenses in connection with p.c. sums or other items, if these have not been priced against respective items.
| (vi) Two blank and one priced copy of these Contract Documents shall be furnished free of cost to the Contractor for his own use. One copy shall be kept on the works until the completion thereof, the Architect and the Quantity Surveyor shall at all reasonable times have access to the same. |  | Item
| Carried to Collection |  |  | K
Page 1/6
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Contract Sum Clause No.13
| The Quantity Surveyor will examine and check the priced Bills of Quantities submitted by any Contractor whose tender is under consideration and he shall be at liberty to call for any correction of any errors so found and for the adjustment of any individual price which he considers unreasonable and for the rectification of any discrepancies as he deems necessary. The tender figure will, however remain unaltered and any necessary correction to make the revised total correspond with the tender figure,will be made,after agreement with the Contractor, by means of a compensating lump sum or percentage increase or decrease. Any such increase or decrease shall be deemed to the cost of builders work including variations and all measured work in the Final Account but shall exclude p.c. and provisional sums which shall remain unaltered |  | Item
B | Materials and Goods unfixed or off site Clause No.14
| The unfixed materials if kept off site, with the permission of the Architect, shall be clearly labelled with identifying marks for the project and should be kept in a safe dry place easily accessed by the consultants for inspection should need arise. |  | Item
C | Practical Completion and Defects Liability Clause No.15
| The Defects Liability Period, unless otherwise stated in Appendix A in Form of Tender shall be six months from the day named in certificate of Practical Completion of the works, but should the defects liability period end during the dry season such period of time shall be extended to include two heavy rain storms plus the time required to make good any damage consequent thereon and plus the time required to include a further testing by two heavy rain storms and any consequent making good. |  | Item
D | Sectional Completion clause No.16
| Where Sectional Completion is required it will be advised in the notes to tenderer in the Form of Tender and the Contractor shall price the same where deemed necessary. |  | Item
E | Assignment or Subletting clause No.17
Should consent be given to sub-let any portion of the works the Contractor will in no way be relieved of his liabilities and responsibilities.
F | Injury to Persons, Property and Employer's Indemnity Clause No.18
The Contractor shall, as stated in the clause, be solely liable for and shall indemnify the Employer against any claims in respect of:-
(i) Injury to persons, including Workmen's Compensation.
(ii) Injury to property.
| Carried to Collection |  |  | K
Page 1/7
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Insurance against Injury to Persons and Property Clause No.19
The Contractor shall, as stated in the clause, be solely liable for and shall indemnify the Employer against any claims in respect of:-
(i) Injury to persons, including Workmen's Compensation.
(ii) Injury to property.
The Contractor shall during the Contract Period without prejudice to his liability arising from Third Party Claims in respect of injury or damage to any person and property or thing, however caused byor arising out of or in connection with the contract, hold the Employer indemnified in respect of any such accident as aforementioned.
Approved insurance shall be effected in the joint names of the Employer and the Contractor against the risks aforesaid with an Approved insurance Company. The indemnity limit in respect of any one accident granted by the stated company in the Appendix to the Form of Tender. The relevant polices and premium receipts are to be submitted to the Architect for scrutiny.
B | Insurance of the Works against Fire etc. Clause No.20
The percentage to be named to cover professional fees shall, unless otherwise stated in the Form of Tender, be 12-11% (12-11 percentage)
Include for complying with Clause 20(A)with regard to risk or loss or damage by fire to new buildings.
Unless otherwise stated in the Form of Tender, Clause 20(B) with regard to Employer accepting risk of loss or damage by fire shall be deemed to be omitted from the Contract. Include, only if so required in the Form of Tender for insuring against loss or damage by fire to any existing structures on the site, as Clause 20(C).
C | Possession, Completion and Postponement Clause No.21
| The Date for possession and Date for completion shall be as agreed in writing at the time of signing the contract |  | Item
| Carried to Collection |  |  | K
Page 1/8
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Damage for Noncompletion clause No.22
| The contractor shall pay to the Employer liquidated and ascertained damages for a period during which the works remain uncompleted the sum as stated in the Form of Tender. |  | Item
B | Extension of Time clause No.23
Sub clause 23(J) shall not be deleted
C | Loss and Expense Caused by Disturbance of Regular Progress of the Works clause No.24
D | Determination by the Employer Clause No.25
E | Determination by the Contractor Clause No.26
F | Nominated Subcontractor clause No.27
| The Contractor shall be responsible for giving all necessary directions to Nominated Sub-Contractors, ascertaining their requirements, coordinating their work and arranging for them to be on site at the proper time for the ordered progress of the Works. He shall place all the orders with Nominated Sub-Contractors clearly on his own behalf and shall not pledge the credit of the Employer either directly or indirectly. In no case shall the contractor be deemed too be the Agent of the Employer nor shall there be created any privity of contract as between the Employer and the Nominated Sub-Contractor. The Contractor must enter into a written Sub-Contract using an approved form and must deposit with the Architect signed copies thereof. |  | Item
The contractor shall accept the responsibility for proving the following services for Nominated Contractors:-
G | General Attendance
(i) Use, for the purpose of the Sub-contract works,of any sc affording belonging to or provided by the contractor while it remains elected upon the site, as long as no warrant or other liability on the part of the contractor or his other sub-contractors shall be created or implied in regard to safety or suitability of the said sc affording.(ii) Provision of water,lighting and watching for the purpose of the Sub-Contract works.(iii) Use of messrooms and sanitary accommodation.(iv) Provision of space for erection of offices or stores or space for storage of plant and materials.(v) Clearing away rubbish produced by them
| Carried to Collection |  |  | K
Page 1/9
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Special Attendance
| (i) Unloading and storing.(ii) Hoisting.(iii) Placing in position.(iv) Providing power.(v) The foregoing services are described hereafter as "Add for attendance etc., as described". Nominated Sub-Contractors shall be responsible for:-(i) The cost of any necessary alteration to or re erection of the Contractor's ordinary scaffolding which may be required by them to carry out their work.(ii) Special Scaffolding.(iii) Provision, erection and removal of workshops, stores, sheds or other buildings for their employees, workmen and materials.(iv) Provision of all necessary plant, tools, materials and equipment, etc., necessary to carry out and complete their work |  | Item
B | Nominated Suppliers clause No.28
The Contractor shall be responsible for placing all orders for materials or goods with Nominated Suppliers clearly on his own behalf and shall not pledge the credit of the Employer either directly or indirectly. He shall arrange for delivery of all materials, goods at the proper time orderly progress of the works.
| The Contractor shall take delivery anywhere in Zambia of all materials or goods supplied by Nominated Suppliers and shall sign a receipt as having received the said materials and goods in good order and condition. He shall offload, transport to site, unload, hoist, provide safe storage and thereafter be responsible for any loss or damage or replacement of any such lost or damaged articles at his own expenses and shall return empty cases if so required. |  | Item
| A Provision is made in the Bills of Quantities following each appropriate p.c. sum for the cost of the foregoing services against items reading "Take delivery and fix only". |  | Item
| All payments by the Contractor for materials or goods supplied must be in full and shall be paid within 30 days of the month during which |  | Item
C | Artists and Tradesmen clause No.29 |  | Item
| Carried to Collection |  |  | K
Page 1/10
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | Certificate and Payments clause No.30
All documents necessary for the purpose of the composition of the Final Account including all documents relating to the accounts of Nominated Sub-Contractors and Suppliers shall be passed to the Quantity Surveyor as and when available during the progress of the works and not later than Three Months after the date of Practical completion.
(i) Clause 30(4B) shall be deemed to be omitted from these Conditions of Contract.
(ii) The value of any materials or goods before delivery to yhe works may not be incuded in the value of Interim Certificates without the Architect's prior written approval.
(iii) Period of Interim Certificates, Honouring Certificates; Percentage of certified value retained;Limit of Retention Fund and period of Final Measurement and Valuation shall be as stated in the Form of Tender.
| (iv) Incude for supporting all claims for Interim Certificate payment with details based on items in the Bills of Quantities together with a list of materials on site with delivered prices extended and such other details as may reasonably be required by the Quantity Surveyor |  | Item
B | Outbreak of Hostilities clause No.32 |  | Item
C | War Damage clause No.33 |  | Item
D | Antiquities clause No.34 |  | Item
E | Arbitration clause No.35 |  | Item
| Carried to Collection |  |  | K
Page 1/11
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
CONTRACTING AND OTHER PARTIES
Employer: Zambia National Commercial Bank Postal address: P.O. Box 33611
Physical Address: Head Office Cairo Road
LUSAKA Code 10101
Tel: 260-211-221380 / 221418 / 236998 Fax: -26 01 223082
E-mail: ..............................................................................
Agents service: Masventures -Architects Contact Person: Bwalya Masabo - 0979313575 Email: masventures09@gmail.com Physical Address: 5819 Lunsmfwa Rd. Kalundu, Lusaka
Agents service: Quantiy Surveyors
Physical Address: 15 Chinsali Court, Landa Road, Northmead, Lusaka/ 4D Chile Street, Kitwe.
Contact Person: Josephine Mutwale - 0977319840 Email: josephinemutwale@gmail.com
| Carried to Collection |  |  | K
Page 1/12
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
CONTRACT DETAILS
Works Description:
The works in this contract is the Proposed Zanaco Branch at Mukuba bussiness Centre, Kitwe including all associated Works
Date on which possession of the site is intended to be given: to be advised
Period for the commencement of the works after the contractor takes possession of the site ........ working days
Completion in sections are required
Intended date of practical completion and the penalty per calender day for the whole of the works: Penalty: To be stated in the Client-Contractor Agreement
A | Dispute resolution
Arbitration/Litigation
| Fixed |  | Item
| Time |  | Item
Arbitration rules as recommended by Zambia Association of Arbitrators
| Carried to Collection |  |  | K
Page 1/13
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
INSURANCES
A | Liability of the Employer
| Insurance is required and the Amount of indemnity for any occurrence or series of occurrences arising out of one event shall be ZMW…………………… |  | Item
B | Insurance for the works
Contract works insurance to be effected by Contractor: For the amount of: ZMW ......................................................... With a deductible of: ZMW...................................................
| Fixed |  | Item
| Time |  | Item
DOCUMENTS
Waivers of contractors lien is required
Yes
Number of construction document copies to be supplied free of charge: ..........................N/A................................
State other system if document is not drawn up in accordance with the Standard System of Measuring Building Work: ................................N/A...................................
Number of days for submission of priced documents: To be advised....................................................................
| Carried to Collection |  |  | K
Page 1/14
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
SECTION "B" SPECIFIC PRELIMINARIES
A | PROPRIETARY BRANDED PRODUCTS The contractor shall take delivery of, handle, store, use apply and/or fix all proprietary branded products in strict accordance with the manufacturers' instruction after consultation with the manufacturer's authorized representative
| Fixed |  | Item
| Time |  | Item
OVERTIME
Should overtime be required to be worked for any reason whatsoever, the costs of such overtime are to be borne by the contractor unless the principal agent has specifically authorized in writing, prior to the execution thereof, that costs for such overtime are to be borne by the employer.
| Fixed |  | Item
| Time |  | Item
AS BUILT DRAWINGS
The position of construction breaks and the extent of individual concrete pours are to be recorded by the contractor on the structural engineer's drawings and are to be submitted to the principal agent and the structural engineer for their records.
| Fixed |  | Item
| Time |  | Item
SITE INSTRUCTIONS
Site instructions issued on site are to be recorded in triplicate in a site instruction book which is to be maintained on site by the contractor
| Fixed |  | Item
| Time |  | Item
| Carried to Collection |  |  | K
Page 1/15
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
LABOUR RECORD
At the end of each week the contractor shall provide the principal agent with a written record, in schedule form, reflecting the number and description of tradesmen and labourers employed by him and all subcontractors on the works each day.
| Fixed |  | Item
| Time |  | Item
PLANT RECORD
At the end of each week the contractor shall provide the principal agent with a written record, in schedule form, reflecting the number, type and capacity of all plant, excluding hand tools, currently used on the works.
| Fixed |  | Item
| Time |  | Item
NON CESSION OF MONIES
The contractor shall not cede nor assign his rights or claims to any monies due or to become due under this contract
| Fixed |  | Item
| Time |  | Item
TEMPORARY FENCING, HOARDINGS, SCREENS, FANS, PLANKED FOOTWAYS, GUARDRAILS AND GANTRIES
The Contractor shall provide and maintain all necessary temporary fencing, hoardings, screens, fans, planked footways, guardrails, gantries and the like for the proper execution of the work, for the protection of the public and the occupants of adjoining premises and for meeting the requirements of any local or other authority, and shall alter, remove, adapt as necessary and finally clear them away when no longer required and shall reinstate all surfaces and services disturbed.
| Fixed |  | Item
| Time |  | Item
| Carried to Collection |  |  | K
Page 1/16
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
VISITORS TO SITE
The Contractor is required to control all visitors to the site and to keep out all unauthorized visitors and to provide a visitors book and ensure that all authorised visitors sign therein.
| Fixed |  | Item
| Time |  | Item
NOTICE BOARD
The Contractor is to provide 1No. Notice Boards in accordance with the requirements of the Project Manager / Architect and erect it where directed
| Fixed |  | Item
| Time |  | Item
ELECTRICAL LIGHT AND POWER
The Contractor shall arrange with ZESCO for a metered supply to the site and shall pay all charges required and shall include all cables, portable leads, fittings and all other materials, plant, equipment and labour.
| Fixed |  | Item
| Time |  | Item
SITE TELEPHONE
The Contractor shall arrange for, provide and maintain a telephone for the use of Consultants and the Clerk of Works upon the site and shall pay all charges required
| Fixed |  | Item
| Time |  | Item
| Carried to Collection |  |  | K
Page 1/17
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
WATER
The Contractor shall provide at his own cost all clean water required for the execution of the contract, include costs of connection, consumption, temporary storage and distribution, all other materials, plant, equipment, labour and comply with the requirements of the Local Authority.
| Fixed |  | Item
| Time |  | Item
SANITATION OF THE WORKS
The sanitation of the works shall be arranged and maintained by the Contractor to the satisfaction of the Architect and Local Authorities The latrines shall be enclosed with framing and corrugated iron roofs, sides and partitions. The site of the latrines shall be agreed with the Architect and the Works shall not be commenced before the sanitary accommodation has been approved by the above- mentioned Authorities.
The Contractor shall provide for the exclusive use of the Consultant and the Clerk of Works ablution facilities consisting of water-borne W.C. suite, wash hand basin complete, approved drainage system, toilet roll hlders, towels, soap etc. and maintain all in satisfactory condition throughout the duration of the contract.
| Fixed |  | Item
| Time |  | Item
SHED FOR STORAGE OF MATERIALS
The Contractor shall provide and maintain on the site ample weatherproof and fire proof shed for storage of cement and other perishable materials and shall clear the same away on completion and make good any disturbed surfaces.
| Fixed |  | Item
| Time |  | Item
| Carried to Collection |  |  | K
Page 1/18
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
SAFETY, HEALTH AND WELFARE
Provide all safety, health and welfare facilities including ensuring the safety of all personnel and visitors on the site and arrange the works with safety as one of the major considerations.
| Fixed |  | Item
| Time |  | Item
PLANT, TOOLS AND VEHICLES
Provide all the plant, tools and vehicles required for the due execution of the whole of the works.
| Fixed |  | Item
| Time |  | Item
SECURITY
Take such measures of protection and security as to avoid tresspass and unrestricted entry, damage want on and inadvertent, theft and injury by and to those whose access to the site is unauthorised paying particular attention to children
| Fixed |  | Item
| Time |  | Item
RUBBISH DISPOSAL
Clear up and remove all rubbish and debris, clean out all pipe ducts as the work proceeds and on completion and leave the buildings and surrounding areas clear of all plant and material.
Remove from site all packing materials and rubbish of an inflammable nature as soon as possible to avoid any danger of fire. Burning of rubbish on site will not be allowed.
Wash down and periodically clear the surface of exposed brickwork concrete and other work, clear all glass inside and out with a wash bather, clear out all gutters, channels and outlets and leave the works on completion in a clean and orderly conditions the Architect's satisfaction.
| Fixed |  | Item
| Time |  | Item
| Carried to Collection |  |  | K
Page 1/19
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
PERSONNEL TRANSPORT
Provide for the transport of personnel to and from the site.
| Fixed |  | Item
| Time |  | Item
SCAFFOLDING
Provide all general scaffolding required for the execution of the works.
| Fixed |  | Item
| Time |  | Item
MANAGEMENT AND STAFF
DIRECTION AND CONTROL
Direct, control and operate with staff in such skills of management, control and supervision needed to realize the conditions of the contract, standards of performance and quality control, with diligence and efficiency to the Architect/ Project Manager's Approval
| Fixed |  | Item
| Time |  | Item
PROTECTION OF WORK
The Contractor shall cover up and protect all finished work liable to damage including provisions of temporary roofs, gutters, drains, etc., until the completion of the works
In the event of any damage occuring to the Works, materials, sewers, drains, gullies, paths or other Works on the Site in temporary possession of the Contractor for the purpose of this Contract, either from the weather, want of proper protection, defects, or insufficiency of the Works or any other cause whatsoever during the progress of the Works, the Contractor alone shall without extra charge, make good all damage and pay all costs which may be levied.
| Fixed |  | Item
| Time |  | Item
| Carried to Collection |  |  | K
Page 1/20
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
DAYWORKS
DAYWORKS
The contractor shall price and extend the following items and prices will be considered as these required by the contractor for the execution of Dayworks if authorized.
Labour rates shall be included for the use of small tools, all aspects of labour costs and the contractor's profit.
Labour
Skilled Worker Class I Hours 20
Skilled Worker Class II Hours 20
Skilled Worker Class III Hours 20
Semi - Skilled Worker Hours 20
Materials
Include the Provisional Sum of ZMW 10,000.00 for materials to be used in Dayworks
Add for Overheads and Profit etc.......% ZMW 10,000.00
Plant and Transport
Include the Provisional Sum of ZMW 10,000.00 for major plant and transport to be used in Dayworks
| Carried to Collection |  |  | K
Page 1/21
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
A | The Contractor shall be deemed to have included in his
rates for the following:-
(i) Making good finishing’s and other works disturbed
(ii) Constant supervision by a Supervisor possessing approved qualifications
(iii) Protection of the works until handed over
(iv) Disposal to authoised dumpsites
B | Allow for complete Preliminary and General Items | Item
___________________________
| Carried to Collection |  |  | K | 0
Page 1/22
BILL NO. 1
PRELIMINARIES AND GENERAL ITEMS
Item | PREAMBLES | Qty | Unit | Rate | K n
COLLECTION PAGE
Page No.
1/1,
1/2,
1/3,
1/4,
1/5,
1/6,
1/7,
1/8,
1/9,
1/10,
1/11,
1/12,
1/13,
1/14,
1/15,
1/16,
1/17,
1/18,
1/19,
1/20,
1/21,
|  |  | 1/22, |  | 0
| BILL NO. 1 TO GENERAL SUMMARY |  |  | K | 0
Page 1/23
BILL NO. 2
DEMOLITIONS AND ALTERATIONS
Item | NOTES: | Qty | Unit | Rate | K n
A | The Contractor is strongly advised to visit the site
| before pricing this section of the works |  | Item
B | All demolition works described herein are shown on Architects Drawings |  | Item
C | The Contractor’s attention is drawn to the fact that the locations used for room areas refers to the existing usage |  | Item
Old Materials required to remain the property of the Employer
D | All salvage materials to be carefully taken down or removed intact, stored safely and later handed to Employer
| Note: Where ever indicated “hand to Client”, this shall mean the owners of the Building |  | Item
E | At the Architect’s discretion, the Contractor may be instructed to re-use some or all of these materials in the new work. |  | Item
F | Should the Contractor however, be interested in the salvage materials, a credit allowance should be indicated in the space provided at the collection page |  | Item
PREAMBLES
G | Demolition works are to be carried out only after express approval has been given by the Architect regarding the proposed method statement of the works. This method statement should be submitted prior to commencement on site and whilst approval will not be unreasonably with held, no claims will be allowed due to a change being imposed on this method statement by the Architect |  | Item
| Carried to Collection |  |  | K
Page 2/1
BILL NO. 2
ALTERATIONS
Item | PREAMBLES (Cont’d) | Qty | Unit | Rate | K n
A | The works have been described in reasonable detail but the Contractor shall consider them in conjunction with the actual work on site and allow for everything necessary for carrying out the works whether specifically mentioned or not
B | The Contractor shall include here or within his rates for making good with materials to match existing any damage that may be caused to adjacent work of whatever kind, during or in consequence of the work as no claim will be entertained for the making good of damage arising from these clauses
Definitions
C | (i) The terms ‘remove’ ‘demolish’ and ‘break out’ shall include for all demolitions, clearing and carting away debris from site unless otherwise directed and for making good all work disturbed
D | (ii) The terms ‘take up’, ‘hack up’ and ‘hack off’ shall include for clearing and carting away all debris from site, making good all work disturbed and preparing backgrounds where directed to properly receive new finish
E | (iii) The terms ‘form openings’ and ‘enlarge opening’ shall include for all necessary demolitions, temporary supports, removal of debris from site, insertion of concrete lintol designed and reinforced at contractor’s desecration and as approved, size to be determined by the thickness of wall, quoining up jambs and making good all finishings as necessary to match existing
| Carried to Collection |  |  | K
Page 2/2
BILL NO. 2
DEMOLITIONS AND
ALTERATIONS
Item | Definitions (Cont’d) | Qty | Unit | Rate | K n
A | (iv) The term ‘block up opening’ shall include for blocking up in blocks or bricks as described removal of waste and making good all work and finishings as necessary to match existing
B | (v) Removing services shall be deemed to include sealing off and making safe and shall include the taking out of equipment, appliances, ancillaries fittings, accessories, brackets, clips supports and the like
Electricity, Water and Telephones
C | (i) The Contractor shall give notice regarding disconnections to the relevant statutory companies prior to any demolitions and shall allow them facilities to remove from the site any fixtures, fittings, or services as may belong to them |  | Item
D | (ii) The Contractor shall allow for liaising with, and providing all necessary attendances on, the authorities concerned in the disconnection of all services |  | Item
Shoring and Supports
E | Allow for all necessary dead or raking shores and other supports as described and for removing and making good on completion |  | Item
Protection
F | The Contractor is to allow for taking all measures necessary for the proper protection of the workforce and public in general and surrounding roads and property |  | Item
| Carried to Collection |  |  | K
Page 2/3
BILL NO. 2
DEMOLITIONS AND
ALTERATIONS
item |  | Qty | Unit | Rate | K n
Redundant Demolition Materials
A | Materials from the demolitions must not be stacked or allowed to accumulate on existing structures in such a way as to cause obstruction or danger |  | Item
Avoidance of Nuisance
B | All demolition, forming of openings etc. are to be carried out in such a manner as to cause as little inconvenience as possible to the occupants of the building and surrounding buildings. It must be noted that the contractor will be held responsible for any claims which may arise from the disregard of this clause |  | Item
C | All rubbish, debris etc. is to be regularly sprinkled with water or such other means as to prevent dust arising |  | Item
Protection of Existing Buildings etc.
D | The Contractor must provide all requisite shores, needles, struts, props or other supports for the necessary protection of the existing building and the supply of all fans, screens and the like for the protection of the general public and in particular any occupants of the buildings. The Contractor shall alter, adapt and maintain all such temporary works as may be necessary from time to time and finally clear away and making good all disturbed. The contractor will be held responsible for the safety of the existing building and the sufficiency of all temporary works |  | Item
| Carried to Collection |  |  | K
Page 2/4
BILL NO. 2
DEMOLITIONS AND
ALTERATIONS
item | Description | Qty | Unit | Rate | K n
Forming New and Blocking Up Openings
A | When cutting or adapting openings through walls for doors, windows, pipework and the like the Contractor shall take particular care not to endanger the stability bearings of beams, joists or any structural difficulties. When during the progress of cutting the existing structure any unforeseen obstruction or unusual circumstance is encountered whereby the effects of proceeding with the work could entail hazard the Contractor shall immediately halt, work, notify the Architect and await instructions |  | Item
B | All making good shall be executed with materials and workmanship to match, in every respect, the surrounding work and is to be properly bonded thereto |  | Item
Preparation of Surfaces
C | Finishings shall include for all making good, keying, levelling and other works necessary to ensure proper and smooth bonding of the new finishings to the existing surfaces |  | Item
Items for Re-use
D | Items described as being ‘handed to Employer’ ‘set aside’ must be removed extremely carefully to avoid damage. The Contractor should allow for any repairs or replacement should any damage occur as or he will be held responsible in this regard |  | Item
| Carried to Collection |  |  | K
Page 2/5
BILL NO. 2
DEMOLITIONS AND
ALTERATIONS
Item | Description | Qty | Unit | Rate | K n
A | Carefully and neatly remove existing door partition size 2983 x 3000mm and hand over to the client. Make good all disturbed works. |  | Item
B | Carefully and neatly remove existing ATM door size 1000 x 2200mm and hand over to the client. Prepare to receive blockwork (M.S). Make good all disturbed works. ATM ROOM |  | Item
C | Carefully and neatly remove existing 3No. doors 900 x 2200mm and hand over to the client. Make good all disturbed works. |  | Item
D | Carefully and neatly remove existing partition overall size 75840 x 3000mm including 14No. 900mm x 2200mm door and hand over to the client. Make good all disturbed works. |  | Item
E | Carefully and neatly remove existing partition overall size75840 x 3000mm including 14No. 900mm x 2200mm door and hand over to the client. Make good all disturbed works. |  | Item
F | Carefully and neatly remove existing 6 No. teller counters including all supporting blockwork, glass screens and the like, handover to client overall length 9000mm. Make good all disturbed works and clear away debris. Bulk teller/Teller counters |  | Item
G | Carefully and neatly remove existing aluminium partition size 2983 x 3000mm including double door and hand over to the client. Prepare to receive new. Make good all disturbed works. Shopfront |  | Item
H | Carefully and neatly remove existing aluminium partition size 4130 x 3000mm including and hand over to the client. Prepare to receive new. Make good all disturbed works. Shopfront |  | Item
J | Carefully demolish existing masonry wall, overall size 1000 x 2200mm, prepare to receive ATM Room security door (M.S) and make good all disturbed work and clear debris. |  | Item
| Carried to Collection |  |  | K | 0
Page 2/6
BILL NO. 2
DEMOLITIONS AND
ALTERATIONS
Item | Description | Qty | Unit | Rate | K n
A | Carefully take out existing 2No. Water Closets and all other associated accesories, handover to client and make good all disturbed works. |  | Item
B | Carefully take out existing 2No. Wash Hand Basins and all other associated accesories, handover to client and make good all disturbed works. |  | Item
C | Carefully take out existing Sink and tap and all other associated accesories, handover to client and make good all disturbed works. |  | Item
D | Allow for propping of beams where necessary |  | Item
E | Make good all existing walls by sanding, skimming with rhinolite and prepare for new fisnish as per wall schedule overall area 650m2 |  | Item
F | Carefully cleanup ceilings, terminate, remove and replace all decomissioned cables |  | Item
G | Carefully hackout existing floor finish and prepare to receive new i.e. leveling existing floors, compacting and grouting before applying new floor finishes. Make good all disturbed works. Overall area 522m2 |  | Item
H | Carefully remove existing light fittings and replace with new ones (measured separately) as per proposed electrical layout. Make good all disturbed works. |  | Item
J | Carefully take down existing ceiling and replace with new ceiling finishes (measured separately) as per proposed ceiling layout overall area 522m2 . Make good all disturbed works. |  | Item
K | Carefully remove existing light fittings and replace with new ones (measured separately) as per proposed electrical layout. Make good all disturbed works. |  | Item
L | Make good glass panels in shopfronts and the like |  | Item
| Carried to Collection |  |  | K | 0
Page 2/7
BILL NO. 2
DEMOLITIONS AND
ALTERATIONS
COLLECTION
|  | Page |  |  | K n
No.
|  | P 2/1 |  |  | 0
|  | P 2/2 |  |  | 0
|  | P 2/3 |  |  | 0
|  | P 2/4 |  |  | 0
|  | P 2/5 |  |  | 0
|  | P 2/6 |  |  | 0
|  | P 2/7 |  |  | 0
| DEMOLITIONS AND ALTERATIONS TO GENERAL SUMMARY |  |  | K | 0
Page 2/8
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
SUPERSTRUCTURE
BLOCKWORK
Hollow concrete blocks in composition
mortar as described
A | 150mm walls | 6 | m² |  | 0
SUNDRIES
B | "Brickforce" or other equal and approved brick reinforcement to suit 150mm walls built into horizontal joints to blockwork | 10 | m |  | 0
C | Damp proof course size 150mm | 4 | m |  | 0
D | Allow for cutting and handpacking in floor slab | 4 | m |  | 0
E | Allow ZMW 1, 000 for cutting, toothing and bonding end of blockwork to existing wall complete with all necessary filling and making good. | 1 | Item |  | 0
One coat plastering as described with steel float finish
F | To concrete, brickwork or blockwork walls | 12 | m² |  | 0
Vibrated reinforced insitu concrete (Grade 25) as described
G | To Lintols and beams | 1 | m3 |  | 0
FORMWORK
Sawn formwork, including making good exposed surfaces after removal of formwork as described to
H | Sides and soffits of lintols, beams, and the like | 23 | m |  | 0
| Carried to Summary page |  |  | K | 0
Page 3/1
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
WALL FINISHES
NOTES;
ALL EXISTING WALL SURFACES TO BE SCRAPPED, MADE GOOD, FILLED AND SANDED PRIOR TO APPLICATION OF FINISH COATINGS
ALL NEW WALL SURFACES TO BE PAINTED WITH 'PLASCON' UNIVERSAL UNDER COAT PRIOR TO APPLICATION OF FINAL PAINT COATING
WF1 - ZANACO APPROVED STONE CLADDING AS 150X600MM RIVEN GLITTERSTONE QUARTZITE INTERLOCKING STONE TILES TO ARCHITECTS APPROVAL
A | To walls | 32 | m² |  | 0
WF2 - Prepare skim and apply two coats "White luxurious silk to match plascon wall and all products range" on the following surfaces:-
B | To walls | 180 | m² |  | 0
WF3 - Gray Approved Luxurious Silk Paint to match Plascon Wall and all Product Range Applied by Specialist to Architects approval
C | To walls, ditto | 333 | m² |  | 0
WF4 - 'MONOCOUCHE M19 TEXTURED PAINT TO LAMASAAT PRODUCT RANGE' WITH MINERAL YELLOW ACRYLIC COVER PAINT. Code;'10YY40/60 TO ARCHITECTS APPROVAL
D | To walls | 40 | m² |  | 0
WF5- Charcoal GRAY NON-SLIP CERAMIC WALL TILES SUPPLIER: HANDYMANS CODE: OMLA20A3ATA
E | To walls | 105 | m² |  | 0
WF6 -Lamasat Wall Textured Paint as 'S-334' with Pebble Black Exterior Weather Guard Cover Paint, Supplier; Lamasaat, Dulux or Plascon to Architects approval
F | To walls | 18 | m² |  | 0
WF7 -Exterior Weather Guard Paint, Supplier; Plascon or Dulux, to Architects approval
G | To walls | 15 | m² |  | 0
| Carried to Collection |  |  | K | 0
P age 3/2
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
FLOOR FINISHES
PREAMBLE
All floor materials to be approved by Client before installation Place aluminium divide strips on all points where carpets abut tiles Place aluminum edge strips around all tiled edges
HEAVY DUTY ZANACO BRANDED RUBBER MAT. LOGO BRAND TO BE SUPPLIED BY WILLIAM SCOTT OR EQUAL TO ARCHITECT'S APPROVAL. To clients preference. Code: LOGO BRANDED
A | Floor tiling laid level on screeded bed as required Size 2m x 1m | 1 | no |  | 0
B | Floor tiling laid level on screeded bed as required Size 1.4m x 1m | 1 | no |  | 0
AMBROSIA (2) BAOBAB BROWN TYPE WOOD FINISHED PORCELAIN FLOOR TILES-Grade A- 150x600 CODE:025-50161506 SUPPLIER: MAKE A HOME.
B | Floor tiling laid level on screeded bed as required | 40 | m² |  | 0
500 x 500mm Artlantis Radiant Carpet Tiles ; Code Artlantis Red; Supplier as Belgotex
C | Floor tiling laid level on screeded bed as required. Place aluminium strips as required | 50 | m² |  | 0
500 x 500mm Berber Point 920 carpet tiles supplied by Belgotex to Architects Approval. CODE-Neutral Brown
D | Floor tiling laid level on screeded bed as required | 81 | m² |  | 0
600 x 600 mm high grade Plain Matte White porcelain floor tiles supplied by Make a Home with aluminium tile trimmers grouting according to the Project Managers Approval - CODE:037-C60812
E | Floor tiling laid level on screeded bed as required. Place aluminium strips as required | 189 | m² |  | 0
600 x 600mm Non-Slips Porcelain Tiles. Colour: Silver Gray; Code; IMI230A; Supplier; Handymany's or to Architects approval.
F | Floor tiling laid level on screeded bed as required. Place aluminium strips as required | 123 | m² |  | 0
Anti-Static Rubber titles
G | Fixed to Cement/Sand floor screed finish | 23 | m² |  | 0
H | 200mm High 600x600x40mm Raised Floor
| On ultra steel frames to Specialist details and Architects details | 8 | m² |  | 0
| Carried to Collection |  |  | K | 0
P age 3/3
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
CEILING FINISHES
Place aluminium edge strips around all edges
A | 1000mm suspended ceiling bulkheads complete with 9mm Rhinoboards installed to specialist detail, skimmed and painted with 3 coats PVA Paint with downlights and double strip L.E.D light beads (Measured separately) | 83 | m²
B | Donn Vanguard Acoustic Ceiling tile size 600 x 600mm in an exposed suspended aluminium grid system complete with all installations and accessories to Architects approval | 522 | m² |  | 0
| Carried to Collection |  |  | K | 0
Page 3/4
BILL NO. 3
MEASURED WORKS
item | Description | Qty | Unit | Rate | K n
DOORS
Cherry Wood Vennered Hardwood Doors with QS '4434' Type coat hanger and 200mm Aluminium kicker plate on both sides to Architects approval.
A | Size 825 x 2160mm | 2 | No. |  | 0
B | Size 725 x 2160mm | 5 | No. |  | 0
Matte-Black Aluminium Frame
C | Size 800/900 x 2200mm aluminium frame | 13 | No. |  | 0
Matte-Black Aluminum Door
D | Size 900 x 2200mm with glazed panels and industrial lock set m/s | 6 | No. |  | 0
SECURITY TYPE CAT.1 DOOR-to be supplied by Zambian Safes and Equipment and FITTED ALUMINIUM FRAME ALL TO ZANACO'S APPROVAL AND MANUFACTURER'S SPECIFICATION
E | Size 1000 x 2300mm 2.3M Profile - CIT ENTRANCE (D4) | 1 | No. |  | 0
IRONMONGERY
Supply and fix the following QS ironmongery complete with matching screws to timber or metal doors and metal or aluminium frames
F | Hafele' type mortice with Approved Yale lockset to Architects Approval | 7 | No. |  | 0
G | Stainless steel door stop, to approval | 13 | No. |  | 0
H | Heavy Duty Steel door stop, to approval of the Architect | 1 | No. |  | 0
J | Rubber door stop, to approval of the Architect | 28 | No. |  | 0
K | Cranked T' type Push Pull Handles with Approved Yale lockset to Architects Approval | 17 | No. |  | 0
L | Supply and Install 'QS 970v type high traffic Door Closer' to doors as indicated | 24 | No. |  | 0
M | 150mm long Yale Stainless Steel hinges to doors | 100 | No. |  | 0
N | 800x200mm Stainless Steel Kick Plates to Architects approval | 14 | No. |  | 0
| Carried to Collection |  |  | K | 0
P age 3/5
BILL NO. 3
MEASURED WORKS
item | Description | Qty | Unit | Rate | K n
ALUMINIUM PARTITIONS
Supply and Install 150mm thick Matte Black anodised aluminium frame partitions with sections 1.5mm profile guage with 6.38mm laminated S30 tinted glass and all with door closers and stainless steel complete with all required accessories. All sizes to be verified on site before manufacture and assembly
A | Laminated aluminum partition size 2965 x 3000mm with 2no. Doors size 900mm x 2200mm with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 1 - Shopfront) | 1 | No. |  | 0
B | Ditto laminated aluminum partition size 3425 x 3000mm with 1 No. door size 900mm x 2200mm with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 2 - Man Trap) | 1 | No. |  | 0
C | Laminated aluminum partition size 1400 x 3000mm with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 3 - Man Trap) | 1 | No. |  | 0
D | Ditto fixed laminated aluminum partition size 6539 x 3000mm (Panel 4 - Managers Office) | 1 | No |  | 0
E | Ditto laminated aluminum partition size 8314 x 3000mm including 1 no. 900x2200mm door. (Panel 5- Meeting Rooms) | 1 | No |  | 0
F | Laminated aluminum partition size 3000 x 3000mm fixed panels with 540 back to back to architects approval (Panel 6 - Meeting Room) | 1 | No |  | 0
G | Laminated aluminum partition size 1874 x 3000mm with 2no. Doors size 900mm x 2200mm with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 7 - Bulk Teller) | 1 | No |  | 0
H | Laminated fixed aluminum partition size 3200 x 3000mm including 1No. 900 x 2200mm door ith 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 8 - Transaction-Meeting Room) | 1 | No |  | 0
J | Laminated fixed aluminum partition size 4027 x 3000mm including 1No. 900 x 2200mm door ith 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 9 - Private Banking-Banking Hall) | 1 | No |  | 0
K | Laminated fixed aluminum partition size 8451 x 3000mm including 1No. 900 x 2200mm door ith 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 10 - Private Banking-Banking Hall) | 1 | No |  | 0
L | Laminated aluminum partition size 6883 x 3000mm with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 11 - Private Banking-Banking Hall) | 3 | No |  | 0
M | Laminated tinted fixed aluminum partition 3No. staggered windows size 2500 x 400mm to architects approval (Panel 12 - Staggered Panels) | 3 | No |  | 0
N | Laminated fixed aluminum partition size 5000 x 3000mm including 2No. 1000 x 2200mm double Sliding door with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 13 - Conference Room) | 1 | No |  | 0
P | Laminated fixed aluminum partition size 5000 x 3000mm including 1No. 900 x 2200mm door with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 14 - Private Banking Entrance) | 1 | No |  | 0
Q | Laminated fixed aluminum partition size 1250 x 3000mm including 1No. 900 x 2200mm door with 540 back to back satin stainless steel door handles with yale lockset to architects approval (Panel 15 - Private Banking MantTrap) | 1 | No |  | 0
| Carried to Collection |  |  | K | 0
P age 3/6
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
DRY WALL PARTITIONS AND DOORS
Unless otherwise described rates for partitions shall be deemed to include for standard flat section aluminium skirtings on both sides
The contractor is to ensure that all nogging are included in the partition system to provide supports for all joinery and sanitary fittings and these must be included in the rates for dry wall.
Dry wall assembled by 75mm fire rated gypsum boards fixed on aluminium plastered stud 2 Hour fire rating drywall partition all as per Manufacturers installation manual including skirting
A | Dry walls to specialist and Architects approval | 115 | m2 |  | 0
JOINERY
B | 90x20mm Hardwood Treated skirting to solid blockwork & drywalling, finished with 2 coats approved quality varnish | 220 | m
Workshop manufactured Kitchen Unit from - GRANITE TOP: - 30 mm thk. with polished and slightly chamfered edges ; CARCASS- Melamine finished MDF; White finish internally; Externally provide sample for clients' selection, DOOR- Melamine finished MDF with 3 mm thk. Arrowline edging matching door colour, HANDLES- 350 mm long stainless steel or satin chrome finished bar handles; and approved all as per Architects Drawing.......................
C | Supply and fit Granite Top Kitchen Unit L-shaped type overall size 2100mm x 600 mm 3350mm x 600 mm deep x 935 mm high; (Meal Nook), 2700 x 600mm deep x 700 mm high wall mounted top units / cupboard, deep drawers all as shown on Architects' Drawing No. .................... | 1 | No.
D | 30 mm thick highly polished granite work top size 1250 x 600 mm complete with steel supporting framing fixed to blockwork | 2 | No.
E | Extra over in granite worktop for sink cut outs of corresponding size | 3 | No.
GLAZING
F | 6mm Float glass in Oak Wood frame, wall mounted; mirror size 1250x800mm high complete with all accessories to Architects approval | 2 | No.
| Carried to Collection |  |  | K | 0
Page 3/7
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
PLUMBING AND SANITARY FITTINGS
Supply and fix as described the following sanitary appliances including jointing to some overflow, waste and soil pipe
A | White glazed ceramic Water closet suite, Low Level, complete with wash down pan with P trap including domex screws, 9 liter ceramic cistern with sides supply fitting and flush pipe, rigid plastic seat and cover and all other accessories | 2 | No.
B | Single bowl and single drain stainless steel sink complete with pillar tap and all othe accessories to Architects satisfaction. | 1 | No.
C | White glazed Vitreous China wash hand basin as 'Jaguar Type' or other equal and approved with and including wall type chromium plated mixer, overflow and waste, fixed with semi - concealed brackets reference 8118, to background plugging, size 585 x 435 mm, complete with all accessories | 2 | No.
D | Standard type Vitreous China toilet roll holder as Vaal 'Regiso'by Potteries (Pty) ltd or other equal and approved, fixing to tiling background with cement - based adhesive, at all water closet suites | 2 | No.
E | Urinals-Vaal Potteries Vitreous China wall mounted "Lavatera" with top inlet (code 704001) or back inlet (code) 704002). Overall size 610 x 385 mm. Supplied with 38 mm Chromium plated domical grating (code 8787), Chromium plated bottle trap, chromium plated spreader (Code 8543), and two hanger brackets (Code 8127), with concealed springbok automatic 4.5 litre syphonic cistern (code 7121) with flush pipe and fittings (code 1722Z1) including concealed flush valves with division pieces (code 7052) (PROVISIONAL) | 4 | No. |  | 0
F | Liquid Soap dispenser | 2 | No. |  | 0
Pipework to Additional Sanitary Fittings
E | Provide a provisional sum of Zambian Kwacha Five Thousand Only for Additional pipework to new Sanitary Fittings |  |  |  | 5000
| Carried to Collection |  |  | K
Page 3/8
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
ELECTRICAL WORKS (ALL PROVISIONAL)
All Electrical works to be carried out by an approved ELECTRICAL SUB-CONTRACTOR
Generally
A | Include for giving all necessary notices, allow for attendances on Zambia Electrical Corporation Ltd for inspection and tests as required by them and the Architect, as described |  | Item
B | Include for all work to be executed as concealed conduit as described except that conduit fixed to roof purlins will be exposed and is to be neatly and accurately positioned with a neat connections made to the concealed conduit in wall using a junction box with center outlet |  | Item
C | Include for the electrical work to be executed by experienced workmen under constant supervision of a qualified tradesman able to speak and write English and competent to correctly interpret relevant drawing and specifications |  | Item
D | Include for providing adequate protection of the installation until handed over taking adequate precautions to protect workmen and public from electric shock or burn |  | Item
Meter & Distribution Boards
Supply, install and connect and set to work the following Distributions Boards as specified and indicated on the Electrical Drawings
Distribution Board - DB BB as shown on Drawing No. ......................; Make EML or equal and approved
E | 32 Way TP+N flush surface mounted with hinged door cover (white in colour) consisting of the following:
| 1No. 80A TP MCB, 2 No.60A TP MCB, 1No. 60A SP MCB, 1No. 40A SP, 3 No.30A SP MCB, 2No. 30A SP MCB Spare, 7 No.20A SP MCB, 3No. SP MCB Spare, 1No.15A SP MCB, 8 No.10A SP MCB, 5No. TP Spare ways, 1No. 20A SP Contactor, 2No. Earth Bar, 1 No. Neutral Bar, 2No. 3 x 10kA Lighting Arrestors | 1 | No. |  | 0
Notes:
The protection of structure against lightning should comply with BSCP326 1965
Joints shall be avoided in the conductors. The necessary tapes shall be overlapped not less than 20 times their thickness and all the edges of the overlap shall be brazed
An earth terminator shall be connected to each down conductor and shall be capable of isolation for testing purposes
| Carried to Collection |  |  | K | 0
Page 3/9
BILL NO. 3
MEASURED WORKS
Item | Description | 1 | Unit | Rate | K n
LIGHTING, SWITCHES & SOCKETS
Supply, deliver, install, connect and set to work the conduits, cables etc for the following Light fittings, sockets, switches, power points including wall mounted socket outlets all as indicated on the drawings. Wiring , cables switching sockets etc all as specified but excluding the supply of Light fittings and Trunking mounted Socket outlets and Hand Dryers, which are measured separately.
A | Supply , Install and connect Signage points in 20mm PVC Conduit, Conduit fittings and 3x1.5mm PVC Single Core cables | 2 | No.
B | Supply , Install and connect light points in 20mm PVC Conduit, Conduit fittings and 3x1.5mm PVC Single Core cables | 191 | No.
C | Supply, install and connect Air Conditioning points in 25mm PVC conduits and conduit fittings c/w 3x4mm PVC Single Core Cables. (Outer Units to be 30m apart with Inner Units in Ceiling space) | 17 | No.
D | Connection to Fire Panel, Circuit | 1 | No.
| 13 Amp Double Switch cabling in trunking | 77 | No.
E | 15 Amp Single Switch cabling | 7 | No.
F | Supply , Install and connect light switches cables | 30 | No.
G | Provide for new supply armoured cable size 50mm x 4 core cable to connect new distribution board position as advised by the PM and set it to work | 45 | m
| Carried to Collection |  |  | K | 0
Page 3/10
BILL NO. 3
MEASURED WORKS
Item | Description | 1 | Unit | Rate | K n
LIGHT SWITCH
Supply, install and set to work the following switches as manufactured by ''LEGRAND" or similar approved including all conduit, conduit, fittings, cable, cable connections and boxes as necessary
A | 10A Two-gang, one-way wall switch, Ref. LEGEND 7300 00 WHI | 2 | No. |  | 0
B | 10A One-gang, one-way wall switch, Ref. LEGEND 7300 00 WHI | 28 | No. |  | 0
POWER POINTS
Supply, install and set to work the following power points including conduits, conduit fittings,cable and connections to connect the power point to the distribution board as manufactured by MK or other equal and approved
C | 13A Double switch socket outlet in trunking with square pin- white colour, as "LEGRAND"(Normal power) | 46 | No. |  | 0
D | Hand dryer C/W 20A DP isolater switch socket at 2200mm AFFL | 2 | No. |  | 0
E | 15A single switch double socket outlet - wall mounted | 4 | No. |  | 0
F | Cooker Control Unit | 1 | No. |  | 0
G | Signage Point | 3 | No. |  | 0
DEDICATED POWER
Supply, instal and set to work the following power points
including all conduit fittings, cable connections to connect
the power points with and including fittings to the Distribution
board with and including 3 core x 2.5mm flex grey cable
H | 13A Double switch scoket outlet in truncking complete with cover, square pine -Red in colour, as "LEGRAND" (Dedicated power) | 31 | No. |  | 0
| Carried to Collection |  |  | K | 0
Page 3/11
BILL NO. 3
| MEASURED WORKS | MEASURED WORKS
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
A | Allow for earthing and bonding the dedicated power cabling including protective earthing at both ends of connections | Item
LIGHTING, POWER AND OTHER FITTINGS
Supply and fix the following lighting, power and other
fittings in accordance with manufacturers instructions
B | 3x18W 600x600mm surface mounted flourescent light fitting c-w ballast and capacitor. | 2 | No. |  | 0
C | E27-100W (1200mm) | 10 | No. |  | 0
D | 600 x 600mm recessed warm white LED Smart type light panels | 113 | No. |  | 0
E | 2 x Pl36 Recessed LED down light fitting as approved by Client | 29 | No. |  | 0
E | 100mm dia 14W (2x7W) Recessed LED down light fitting as approved by Client | 35 | No. |  | 0
E | 600mm dia LED light pendant ring as approved by Client | 2 | No. |  | 0
F | 36W Neon Cool Red L.E.D Lighting double strip beads in 20mm Approved quality P.V.C Casing Tubes Fixed/Glued to Gypsum Bulkhead to Architects Approval | 54 | m |  | 0
TRUNKING, CABLE DUCTS AND THE LIKE
Metal or any other equal approved trunking, cable trays
and service boxes as manufactured by FIRST TECH or
similar and approved
G | 166 x 55mm wide three compartment, two cover pvc trunking plugged and screwed to brickwork walls or drywalling, as "LEGRAND"(brnaching off +sockets ) | 54 | m |  | 0
H | Supply and install Data Cable Tray securely fixed to underside roof members as per specialist, make and set to make the system work to the approval of the Architect | 79 | m |  | 0
J | Supply and install Security Cable Tray securely fixed to underside roof members as per specialist, make and set to make the system work to the approval of the Architect | 84 | m |  | 0
K | Extra Over ditto for end cap, "LEGRAND" | 5 | No. |  | 0
L | Extra Over ditto for internal/external elbow, as "LEGRAND" | 12 | No. |  | 0
M | Allow for earthing and bonding the dedicated power cabling including protective earthing at both ends of connections | Item
N | Allow for rewiring of existing Electrical Distribution board for small power | 1 | No |  | 0
O | Supply and Install HUB [PABX] panel complete with telephone as per Engineers Instructions | 1 | No. |  | 0
P | Allow for existing Auxilliary Distribution Board to be rewired, connect and set to work with all the accessories Engineer to coordinate on site | 1 | No. |  | 0
| Carried to Collection |  |  | K | 0
Page 3/12
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
Dedicated power (Cont'd)
LIGHTING, POWER AND OTHER FITTINGS
TELEPHONE AND COMPUTER INSTALLATIONS
COMPUTER POINTS
Supply and install the following computer terminal socket
points including all conduits and conduit fittings,
cables to connect the socket to Hub, including
leaving all draw-wires as manufactured by LEGRAND or MK
and O-Line or ther equal and approved
A | Computer data outlet in trunking wall Ref. RJ45 CAT 6, as "LEGRAND MOSAIC' 74826 + 75027 | 37 | No.
B | Single telephone outlet point in trunking wall - RJ45 CAT6, "LEGRAND MOSAIC" 74826 +75027 | 8 | No.
C | Cat 6A Network Cable (500 mtrs) | 8 | No.
D | 48 Port Patch Panel CAT 6A | 7 | No.
E | 32 U Free Standing Cabinet | 1 | No.
F | Patch Panel Cat 6 A | 4 | No.
G | Brush Panel | 4 | No.
H | Fly Lead Cat 6 A | 45 | No.
J | Patch Cord Cat 6 A | 45 | No.
K | Media Convertor MM 1000Fx/Rx | 2 | No.
L | Pigtail | 2 | No.
M | Cat 6 A Utp Cable (500m) Drum | 25 | No.
| Carried to Collection |  |  | K
Page 3/13
BILL NO. 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
CCTV, ACCESS CONTROL AND ALARM SYSTEM
Equipment and wiring to be carried out by specialists engaged directly by the Contractor and Approved by the Project Managers
Builders work in connection
A | Allow for Builders works associated with Security Installations Generally | 1 | Item
B | Allow for General Attendance to associated with Security Installations Generally | 1 | Item
| Carried to Collection |  |  | K | 0
Page 3/14
BILL NO 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
AIR-CONDITIONING SERVICES INSTALLATIONS
Equipment and wiring to be carried out by specialists engaged directly by the Contractor and Approved by the Project Managers
Builders work in connection
A | Allow for Builders works associated with Air-conditioning Installations Generally | 1 | Item
B | Allow for General Attendance to works associated with Airconditioning Installations Generally | 1 | Item
| Carried to Collection |  |  | K | 0
Page 3/15
BILL NO 3
MEASURED WORKS
Item | Description | Qty | Unit | Rate | K n
FIRE ALARM, SMOKE DETECTION AND SECURITY ALARM RETICULATION
Supply, deliver, install & set to work the following Fire Alarm Panel and accessories
(All cables for Fire alarm reticulation to be Fire resistant)
A | Fire alarm panel 4 zone as 'GENT' 3260-4 | 1 | No. |  | 0
B | Manual fire alarm breakglass unit as 'GENT' 14112-18 | 4 | No. |  | 0
C | Fire alarm bell -6" as 'GENT' 12511-18 | 4 | No. |  | 0
D | Smoke detector as 'GENT' 17630-01 | 27 | No. |  | 0
E | Heat detector as 'GENT' 12511-18 | 1 | No. |  | 0
F | Supply and install Fire Extinguisher | 17 | No. |  | 0
G | Supply, install and connect Beacon | 3 | No. |  | 0
H | Fire Blanket to Architects approval | 1 | No. |  | 0
J | 25mm PVC Conduit 4 Core Comms Cable for alarm | Item |  |  | 0
K | Provide Jason approved type First Aide Kit to the satisfaction of the Architect | 1 | No. |  | 0
L | Fire Resistant approved Fire Cable in conduiting to fittings | 39 | No. |  | 0
M | Decommission Existing Alarm detection system | 1 | Item |  | 0
N | Provide approved quality Fire Escape Route Signage as guided | 21 | No.
P | Provide approved quality Fire Extinguisher Signage as guided | 17 | No.
| Carried to Collection |  |  | K | 0
Page 3/16
COLLECTION PAGE
Item |  | Qty | Unit | Rate | K n
|  | Page |  |  | COLLECTION
|  | No |  |  | K n
|  | P3/1 |  |  | 0
|  | P3/2 |  |  | 0
|  | P3/3 |  |  | 0
|  | P3/4 |  |  | 0
|  | P3/5 |  |  | 0
|  | P3/6 |  |  | 0
|  | P3/7 |  |  | 0
|  | P3/8 |  |  | 0
|  | P3/9 |  |  | 0
|  | P3/10 |  |  | 0
|  | P3/11 |  |  | 0
|  | P3/12 |  |  | 0
P3/13
P3/14
P3/15
|  | P3/16 |  |  | 0
BILL NO.3
MEASURED TOTAL CARRIED
| WORKS TO SUMMARY |  |  | K | 0
Page 3/17
BILL NO 4
MEASURED WORKS
Item | PRIME COST AND PROVISIONAL SUMS | Qty | Unit | Rate | K n
A | Allow provisional sum of ZMW 20, 000.00 for attendance to making good to walls and electricals as a result of Furniture Installation Works as approved by the Architect |  | Item |  | 20000
B | Allow provisional sum of ZMW 20, 000 for attendance to making good to walls and electricals as a result of Branding Works as approved by Architect |  | Item |  | 20000
C | Allow a Provisional Sum of ZMW 30, 000 only for any supporting temporary Branch relocation works to be directed by the Architect |  | Item |  | 30000
E | Allow a Provisional Sum of ZMW 20, 000 for any additional Private Banking Works, to be directed by the Architect |  | Item |  | 20000
F | Allow a Provisional sum of ZMW 30, 000 only for Entrance canopy works around the Branch Entrance |  | Item |  | 30000
| Carried to Collection |  |  | K | 120000
Page 4/1
PROPOSED ZANACO MUKUBA MALL BRANCH
KITWE
GENERAL SUMMARY
Page
|  | No. |  |  | K n
| BILL NO. 1 PRELIMINARIES & GENERAL ITEMS | P1/23 |  |  | 0
| BILL NO. 2 DEMOLITION WORKS | P2/11 |  |  | 0
| BILL NO. 3 MEASURED WORKS | P3/17 |  |  | 0
| BILL NO. 4 PRIME COSTS AND PROVISIONAL SUMS | P4/1 |  |  | 120000
| SUB TOTAL |  |  | ZMW
| ADD Contigency @10% |  |  | ZMW | 0
| SUB TOTAL |  |  | ZMW | 0
| ADD: VALUE ADDED TAX @ 16% |  |  | ZMW | 0
| GRAND TOTAL TO FORM OF TENDER |  |  | ZMW | 0
GS/1