## VALUATION (hidden)
HONG CHEN CONSTRUCTION LIMITED
CLAIM NO. 03
| PROJECT MANAGER: ZANACO |  | CONTRACT: PROPOSED REFURBISHMENT WORKS
AT ZANACO HEAD OFFICE 8TH FLOOR
| CONTRACTOR: HONG CHEN CONSTRUCTION LTD |  | CONTRACT SUM (VAT INCLUSIVE) |  | 3300638.1
PLOT NO. 225 MAPOSA ROAD, CHAMBA VALLEY,
LUSAKA - ZAMBIA
DATE OF CLAIM: 17/11/2020
| VALUATION FOR FINAL ACCOUNT CERTIFICATE NO. | 3
|  | A CONTRACT SUM | B CURRENT CONTRACT VALUE | C CURRENT VALUATION | D CURRENT AMOUNT CERTIFIED
1 | Value of Work Executed |  |  | #REF!
2 | Materials on Site |  |  | 0
3 | Materials off Site
4 | Less: Retention @ 5% |  |  | #REF!
5 | Add: Advance Payment
6 | Net Contract Sum (without VAT) | #REF!
7 | Authorised Adjustments
8 | Contract Price Adjustment | #REF! |  | #REF! | #REF!
9 | GROSS AMOUNT AMOUNT CERTIFIED |  |  |  | #REF!
10 | Less: Liquidated damages | 100% |  |  | 28000
11 | Less: Previous Amount Certified before VAT |  |  |  | 1862744.46
| NET AMOUNT CERTIFIED |  |  |  | #REF!
12 | Less: Contract Claims |  |  |  | 0
| SUB-TOTAL | #REF! |  |  | #REF!
13 | Add: VAT @ 16% | #REF! |  |  | #REF!
| TOTAL | #REF! |  |  | #REF!
14 | AMOUNT NOW DUE TO THE CONTRACTOR IN THIS VALUATION (ZMK) |  |  |  | #REF!
The above net valuation is issued, without prejudice to its amendments, in accordance with the conditions of contract and is
subject to all materials and workmanship to which it relates being approved.
| COPY: Project Manager |  | …………………………………………………………
Contractor
Employer

## 3rd Floor
Item | Description | Unit | Boq Qty | Rate | Boq Amount
Proposed Refurbishment Works to the 3rd Floor, Zambia National Commercial Bank Headquarters, Cairo Road, Lusaka.
Bill Nr 2 : Third Floor Refurbishment Works
Element 1 Demolition Works
NATURE OF THE WORK
The bidder is advised to conduct a site visit before pricing this document
A | The bidder is advised to visit the site and satisfy himself as to the extent and nature of the works. The Contractor must conform to the instructions of the Client in carrying out any portion of the work which in his opinion requires to be expedited and the Contractor shall give priority to such work as and when directed
SAFETY
B | High safety standards shall be observed for the whole duration of the works
ELECTRIC WIRES, PIPES, ETC
C | Special care is to be taken not to interfere unnecessarily with any electric light, power or telephone wires and fittings that may be met with and notice is to be given to the Client when any disconnections or removal of wires etc are necessary, and the contractor is to afford every facility to the person carrying out this work.
D | Any water supply, waste or other piping that may be met with and found necessary to disconnect or cut are to be effectively stopped off and any new connections that may be necessary are to be made with proper fittings and to the satisfaction of the Client to whom due notice must be given of any alterations to the existing services
PROTECTION
E | In taking down and removing existing work utmost care is to be taken to avoid any structural or other damage to the remaining portions of the building, and the work is to be carried out in a workmanlike, practical and safe manner, under the constant supervision of a competent foreman. The Contractor must also protect all work not removed such as walls, floors, doors, windows, or other joinery, loose and fixed fittings and electrical appliances etc. from damage during the progress of the work and provide all necessary materials for doing so. The Contractor will be held responsible for any damage to persons or property and for the safety of the structure throughout the whole of this contract and must be made good at his own expense any damage that may occur.
MATERIALS FROM DEMOLITIONS
F | All the materials from demolitions are to become the property of the Client, except where stated otherwise, and can only be removed from site and CREDIT is to be allowed for the same under the work section stated once the Client advises so
G | Any sound material which is in good condition may, with the Client's written consent, be re-used. Old materials specified to be set aside for re-use are to be carefully removed, cleaned, stored, protected and made good as required
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Boq Qty | Rate | Boq Amount
DISTURBANCE, DUST AND NOISE PROTECTION
A | The Bank will continue to operate throughout the construction works Contract and the Contractor will be required to carry out the work in the most careful manner so as to minimise noise, inconvinience and disturbance to the public and all neighbourhood. The Contractor is to supply , install or erect all equipment and materials necessary for the complete dust protection of all areas in operation during the execution of work in such areas to the satisfaction of the Client and remove when directed. Elevators shall not be the means of delivering materials to the Sites.
NOTICES
B | Give all notices to the Municipality and/or Authorities and pay charges legally payable and include for the removal or alteration or disconnection of electric wires or cables, telephone wires, etc, which may be met
DEMOLITION WORKS
A | Carefully reuse the existing installations and fixtures together with associated works, data and electrical cables, data points and sockets and prepare workplace for touch up |  | 1 |  | 0
B | Include provisional for additional demolition works and set aside as directed by the Client | item | 1 |  | 0
Element 2 Refurbishment and New Works
CARPENTRY, JOINERY AND IRONMONGERY
| Provision for attendance to lekage and Ceiling works | Item | 1
Kitchen Unit/Cabinets
A | Provision for Builders Works concerning extension of Toilet as is on the 6th & 7th Floors, for Clients Approval | Item | 1 |  | 0
B | Supply and fix 2,500 x 590 x 1000mm shaped standard medium density fibre board New Kitchen unit complete with sink and granite vanity top approved by the Client | Item | 1 |  | 0
C | In Bathrooms, Supply and fix White glazed vitreous china drop- in wash hand basin as Vaal Sola or other equal and approved complete with 1 Nr. 15 mm high neck pillar tap as Jaguar, plastic plug, chromium plated chain and 32 mm waste supported on 30mm polished and edged granite top, size 1600 x 600 mm complete with Backsplash | No | 2 |  | 0
0
D | Supply and fix approved Hand drier | No | 4 |  | 0
D | Supply and fix approved Water closet/Toilet | No | 6 |  | 0
E | Supply and fix approved Urinal | No | 3 |  | 0
| Fittings |  |  |  | 0
0
E | 6mm Polished float glass silvered mirror and fixing to wall with double sided tape and chrome plated dome screws. Size 1600 x 2100mm, Complete with Led strip or Back illumination as directed by client | No | 2 |  | 0
0
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Boq Qty | Rate | Boq Amount
| FLOOR, WALL AND CEILING FINISHES |  |  |  | 0
0
A | Supply and fix heavy duty rubberised carpet tiles, Belgotex Heavy Commercial Induna -Mpande and Mswati carpet tiles on screeded floors to manufacturers detail and specifications | m2 | 846 |  | 0
B | Supply and fix Ceramic floor (Bathroom) tiles to manufacturers detail and specifications | m2 | 28 |  | 0
0
C | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails | m2 | Omitt
0
D | Supply and fix 300 x 600mm white glazed wall tiles with approved adhesive up to 2m high in the Toilets | m2 | 126.9 |  | 0
0
F | Expose and rectify leaks in the walls | item | 1 |  | 0
0
G | Supply and fix 300 x 600mm white/Grey glazed wall tiles with approved adhesive up to 600mm high in the Kitchen | m2 | 2 |  | 0
0
H | Supply and fix 600 x 600mm white/grey ceramic floor tiles with approved tile fix/adhesive in the Kitchen | m2 | 6 |  | 0
0
| Provide Seventy thousand Provisional Sum formaking good and adding to Existing to ceiling | Item | 1 | 70000
|  | TO SUMMARY ZMK |  |  | 0
Item | Description | Unit | Boq Qty | Rate | Boq Amount
PAINTING AND DECORATING
Prepare and apply one undercoat and three coats PVA ZANACO warm white paint on the following surfaces as described
A | Supply and paint plastered walls and Doors in two coats Luxurious Silk, necessary undercoat, Zanaco approved paint | m2 | 231 |  | 0
0
B | To existing door frames | m2 | 20 |  | 0
C | Apply two coats textured paint to surfaces of column,walls and dry walls | m2 | 70 |  | 0
0
D | Provide Provisional Sum of 25000 for Interior design Decorations Services as Instructed By Client | Item | 1 | 25000
0
TO COLLECTION ZMK
Item | Description | Unit | Boq Qty | Rate | Boq Amount
ELECTRICAL INSTALLATIONS
LIGHT FITTINGS
The following light fittings inclusive of lamp, starter, flexible cord and the like
A | Supply and fix 600 x 600mm,LED light panels with , Approved by Client | No | 180 |  | 0
0
0
D | Supply and fix 4 x 36W, 1200mm long recessed mounted batten fluorescent light fitting with cool white tube with metallic body, start gear as PHILIPS TBS 269 4 x 18 W ELB recessed fluorescent C/W LBR diffuser | No | 5 |  | 0
0
E | Provide Power poles complete with sockets to workstations | No | 8 |  | 0
|  | TO SUMMARY ZMK |  |  | 0
Item | Description | Unit | Boq Qty | Rate | Boq Amount
ALUMINIUM WORKS
Doors and entrance screens in Black factory coated aluminium glazed with 6.38mm thick laminated clear glass fixed with lugs and raw bolts, wedged and silicon sealant to glazing on spacers and setting blocks including all ironmongery and build in as described
A | Supply and fix Approved aluminium section in single shopfront doors comprising 1 No. open able light size 900 x 2000mm each with high Black approved aluminium frame, glazing thickness 6.4mm laminated safety glass,with butt hinges, handles, lock, door type AD2 overall size 900 x 2400mm, 400mm louvered on top | m2 | 10 |  | 0 | 10.8
Partitioning in Black aluminium framing glazed with 6.38mm clear laminated safety glass (Doors and Entrance screens measured separately)
B | Supply and fix 2.8metres high in three rows and vertical frames not exceeding 1metre centres top row 600mm high in 4 no. 6.38mm frosted louvre blades laminated safety glass, and middle row 1,100mm and 1,100mm bottom row in 6.38mm frosted aluminium glazing together with aluminium framing in full height, Zanaco branded up to 1200mm height | m2 | 109.2 |  | 0
0
| Dry Wall |  |  |  | 0
| Dry wall assembled by 75mm fire rated gypsum boards fixed on aluminium plastered stud 2 Hour fire rating drywall partition all as per Manufacturers installation manual including skirting |  |  |  | 0
0
C | Supply and fix 2.8x5 metres high partiotion complete with 4 staggered Aluminium framed lights not exceeding 2m2 in safety glass. | item | 8 |  | 0
0
0
0
D | Hardwood Skirting | m | 132 |  | 0
|  | TO SUMMARY ZMK |  |  | 0
A | DEMOLITION WORKS
B | CARPENTRY, JOINERY AND IRONMONGERY |  |  |  | 0
C | FLOOR, WALL AND CEILING FINISHES |  |  |  | 0
D | PAINTING AND DECORATING |  |  |  | 0
E | ELECTRICAL INSTALLATIONS |  |  |  | 0
F | Aluminium & Dry Walls |  |  |  | 0
| Subtotal 1 | K |  |  | 0
| Contigency 5% |  |  |  | 0
| Subtotal 2 |  |  |  | 0
| VAT 16% |  |  |  | 0
| Total Sum to Form of Tender | K |  |  | 0

## Blinds (hidden)
WAMUBA CONSTRUCTION CIVIL CONTRACTORS P.O. BOX UTH 37 LUSAKA TEL/CELL: +260977720972/0966720972 Plot No. 39, Ngwerere Road, Lusaka
Quote to: Zambia National commercial Bank Lusaka |  |  |  | QUOTATION
24th December,2021
Quote No. 2021/10/4
Item | Description | Unit | QTY | Rate | Amount(ZMW)
A | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails on 15th Floor | m2 | 128 | 1000 | 128000
B | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails on 10th Floor | m2 | 128 | 1000 | 128000
C | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails on 9th Floor | m2 | 128 | 1000 | 128000
D | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails on Mezzanine Floor | m2 | 128 | 1000 | 128000
|  |  |  | Sub Total | 512000
|  |  |  | add 16%VAT | 81920
|  |  |  | Total | 593920
|  |  |  | Validity: | 30days
|  |  |  | Delivery Period: | 4 (four) Weeks
Wamuba Construction Limited