## VALUATION (hidden)
HONG CHEN CONSTRUCTION LIMITED
CLAIM NO. 03
| PROJECT MANAGER: ZANACO |  | CONTRACT: PROPOSED REFURBISHMENT WORKS
AT ZANACO HEAD OFFICE 8TH FLOOR
| CONTRACTOR: HONG CHEN CONSTRUCTION LTD |  | CONTRACT SUM (VAT INCLUSIVE) |  | 3300638.1
PLOT NO. 225 MAPOSA ROAD, CHAMBA VALLEY,
LUSAKA - ZAMBIA
DATE OF CLAIM: 17/11/2020
| VALUATION FOR FINAL ACCOUNT CERTIFICATE NO. | 3
|  | A CONTRACT SUM | B CURRENT CONTRACT VALUE | C CURRENT VALUATION | D CURRENT AMOUNT CERTIFIED
1 | Value of Work Executed |  |  | #REF!
2 | Materials on Site |  |  | 0
3 | Materials off Site
4 | Less: Retention @ 5% |  |  | #REF!
5 | Add: Advance Payment
6 | Net Contract Sum (without VAT) | 2845378.28
7 | Authorised Adjustments
8 | Contract Price Adjustment | 2845378.28 |  | #REF! | #REF!
9 | GROSS AMOUNT AMOUNT CERTIFIED |  |  |  | #REF!
10 | Less: Liquidated damages | 100% |  |  | 28000
11 | Less: Previous Amount Certified before VAT |  |  |  | 1862744.46
| NET AMOUNT CERTIFIED |  |  |  | #REF!
12 | Less: Contract Claims |  |  |  | 0
| SUB-TOTAL | 2845378.28 |  |  | #REF!
13 | Add: VAT @ 16% | 455260.5248 |  |  | #REF!
| TOTAL | 3300638.8048 |  |  | #REF!
14 | AMOUNT NOW DUE TO THE CONTRACTOR IN THIS VALUATION (ZMK) |  |  |  | #REF!
The above net valuation is issued, without prejudice to its amendments, in accordance with the conditions of contract and is
subject to all materials and workmanship to which it relates being approved.
| COPY: Project Manager |  | …………………………………………………………
Contractor
Employer

## MAIN SUMMARY
MAIN SUMMARY
CONTRACT SUM (VAT Exclusive) :
| CONTRACT SUM (VAT Exclusive) : |  | 2845378.28
|  |  | 2845378.28 | 258670.75
Data : 9/05/2021
SECTION 1 : PRELIMINARIES & GENERAL
1 | Perliminarise and General Items | #REF!
#REF!
SECTION 2 : BUILDERS WORK
2 | Value of Measured Works Executed 6th floor ( Less 17.25% Discount) | #REF!
3 | Value of Measured Works Executed 7th floor (Less 17.25% Discount) | #REF!
4 | Provisional sum | #REF!
#REF!
SECTION 3 : VARIATION ORDERS
5 | Variations | #REF!
#REF!
#REF!
SECTION 4 : MATERIALS ON SITE
6 | Materials on/off site |  | 0
#REF!
7 | Less: Retention @ 5% |  | #REF!
#REF!
| Add: Retention at 100% |  | #REF!
8 | Add: Advance Payment without VAT
#REF!
10 | Less: Liquidated Damages for 31 days. |  | -27535.9188
#REF!
11 | Less: Previously Certified Total (Advance Payment ) |  | #REF!
12 | AMOUNT NOW RECOMMENDED FOR PAYMENT BEFORE VAT |  | #REF!
13 | Add: VAT @ 16% |  | #REF!
14 | AMOUNT NOW RECOMMENDED FOR PAYMENT |  | #REF!
#REF!

## Completion Certificates
Certificate of
COMPLETION
Employer | : ZANACO
Address | : P O Box 31936, Lusaka
Contractor | : HONG CHEN CONSTRUCTION LTD
Address | Kamanga, Lusaka
Lusaka
Works | : Refurbishment of 6th & 7th Floor
Situates | : ZANACO HEADOFFICE, Cairo Rd.
Lusaka
Under the terms of the above-mentioned Contract,
Upon rectification of snags, we certify that the project works (Refurbishment of a branch) were completed on
15th Septermber 2020
Signed……………………………….……………………………………………………………
The Project has been delivered complete
CERTIFICATE of PRACTICAL COMPLETION
Employer | : ZANACO
Address | : P O Box 31936, Lusaka
Contractor | : HONG CHEN CONSTRUCTION LTD
Address | Kamanga, Lusaka
Lusaka
Works | : Refurbishment of 6th & 7th Floor
Situates | : ZANACO HEADOFFICE, Cairo Rd.
Lusaka
Under the terms of the above-mentioned Contract,
Upon occupation of the floors with excetion of rectification of minor snags, we certify that the project works (Refurbishment of 6th & 7th Floors) were completed on:
05th MARCH 2021
Signed……………………………….……………………………………………………………
The Project has been delivered complete

## 15th Floor
Item | Description | Unit | Qty | Rate
Amount K n
Proposed Refurbishment Works to the Executive 15th Floor, Zambia National Commercial Bank Headquarters, Cairo Road, Lusaka.
Bill Nr 2 : 15th Floor Refurbishment Works
Element 1 Demolition Works
NATURE OF THE WORK
The bidder is advised to conduct a site visit before pricing this document
A | The bidder is advised to visit the site and satisfy himself as to the extent and nature of the works. The Contractor must conform to the instructions of the Client in carrying out any portion of the work which in his opinion requires to be expedited and the Contractor shall give priority to such work as and when directed
SAFETY
B | High safety standards shall be observed for the whole duration of the works
ELECTRIC WIRES, PIPES, ETC
C | Special care is to be taken not to interfere unnecessarily with any electric light, power or telephone wires and fittings that may be met with and notice is to be given to the Client when any disconnections or removal of wires etc are necessary, and the contractor is to afford every facility to the person carrying out this work.
D | Any water supply, waste or other piping that may be met with and found necessary to disconnect or cut are to be effectively stopped off and any new connections that may be necessary are to be made with proper fittings and to the satisfaction of the Client to whom due notice must be given of any alterations to the existing services
PROTECTION
E | In taking down and removing existing work utmost care is to be taken to avoid any structural or other damage to the remaining portions of the building, and the work is to be carried out in a workmanlike, practical and safe manner, under the constant supervision of a competent foreman. The Contractor must also protect all work not removed such as walls, floors, doors, windows, or other joinery, loose and fixed fittings and electrical appliances etc. from damage during the progress of the work and provide all necessary materials for doing so. The Contractor will be held responsible for any damage to persons or property and for the safety of the structure throughout the whole of this contract and must be made good at his own expense any damage that may occur.
MATERIALS FROM DEMOLITIONS
F | All the materials from demolitions are to become the property of the Client, except where stated otherwise, and can only be removed from site and CREDIT is to be allowed for the same under the work section stated once the Client advises so
G | Any sound material which is in good condition may, with the Client's written consent, be re-used. Old materials specified to be set aside for re-use are to be carefully removed, cleaned, stored, protected and made good as required
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
DISTURBANCE, DUST AND NOISE PROTECTION
A | The Bank will continue to operate throughout the construction works Contract and the Contractor will be required to carry out the work in the most careful manner so as to minimise noise, inconvinience and disturbance to the public and all neighbourhood. The Contractor is to supply , install or erect all equipment and materials necessary for the complete dust protection of all areas in operation during the execution of work in such areas to the satisfaction of the Client and remove when directed. Elevators shall not be the means of delivering materials to the Sites.
NOTICES
B | Give all notices to the Municipality and/or Authorities and pay charges legally payable and include for the removal or alteration or disconnection of electric wires or cables, telephone wires, etc, which may be met
DEMOLITION WORKS
Lay-in Ceiling
C | Carefully remove the existing ceiling panels together with associated works, light fittings, make good works disturbed, clear away from site and prepare to receive new ceiling works | m2 | 430 |  | 0
Partition
D | Demolish glazed aluminium partion approximately 4.5 x 2.8m high, make good works disturbed and clear away debris from site as directed by Client ( ELEVATOR LOBBY) | Item | 1 |  | 0
E | Carefully remove the existing drywall timber partition walls together with associated works, make good works disturbed, clear away debris from site and prepare to receive new aluminium partitions | m2 | 90 |  | 0
F | Carefully sand down and prepare drywall partition walls to receive new zanaco warm white paint (Or any approved by Client) | m2 | 0 |  | 0
Sanitary fittings
G | Carefully remove the existing disfunctional geyser with associated pipes and accessories and prepare surface to make good in the kitchen and store as directed by client | item | 1 |  | 0
H | Carefully remove the existing disfunctional geyser with associated pipes and accessories and prepare surface to make good in the toilets and store as directed by client | item | 1 |  | 0
I | Carefully remove the existing watercloset together with cistern with associated pipes and accessories and prepare surface to receive new water closets and store as directed by client | item | 3 |  | 0
J | Carefully remove the existing wash hand basins with associated pipes and accessories and prepare surface to receive new wash hand basins and store as directed by client | item | 4 |  | 0
K | Carefully remove the existing hand driers with associated accessories and prepare surface to receive new hand driers and store as directed by client | item | 2 |  | 0
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
A | Carefully remove the existing soap dispensers with associated accessories and prepare surface to receive new soap dispensers and store as directed by client | item | 4 |  | 0
B | Carefully remove the existing toilet roll holders with associated accessories and prepare surface to receive new toilet roll holders and store as directed by client | item | 3 |  | 0
C | Carefully remove the existing urinals with associated pipes and accessories and prepare surface to receive new urinals and store as directed by client | item | 3 |  | 0
D | Carefully remove the existing kitchen sink with associated pipes and accessories and prepare surface to receive new drop in sink and store as directed by client | item | 1 |  | 0
Floor, Wall tiling and finishes
F | Carefully remove the existing floor finish together with associated works, make good all work disturbed and prepare to receive new directed by the Client | Item | 1 |  | 0
G | Carefully remove the existing white glazed wall tiles together with associated works, make good all works disturbed and prepare to receive new wall tiles in the Toilets, store as directed by the Client | m2 | 130 |  | 0
H | Carefully sand down and prepare plastered walls to receive new zanaco warm white paint | m2 | 130 |  | 0
Doors
I | Carefully remove existing 725 x 1960mm doors and prepare receive new doors to the toilets and store as directed by client | No | 9 |  | 0
J | Carefully remove the existing 825 x 1960mm door and prepare receive new door to the kitchen and store as directed by client | No | 1 |  | 0
K | Carefully remove the existing 825 x 1960mm door together with frames mounted on partition walls in offices and prepare to receive new doors and store as directed by client | Item | 11 |  | 0
L | Carefully remove the existing double door together with frames mounted on partition walls in conference Room and prepare to receive new doors and store as directed by client | Item | 1 |  | 0
M | Carefully remove the existing double aluminium door together with frames mounted on partition walls at the Entrance from the Foyer and prepare to receive new doors and store as directed by client | Item | 3 |  | 0
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
A | Carefully remove the existing airconditioners with associated external units and accessories and prepare surface to make good and keep for reuse as directed by client | item | 6 |  | 0
Electrical Installations
B | Carefully reuse the existing metal trunking together with associated works, data and electrical cables, data points and sockets and prepare to receive new trunking | Item | 1 |  | 0
C | Carefully reuse the existing wall mounted data points with associated cables and accessories and prepare surface to receive new ones and store as directed by client | Item | 1 |  | 0
D | Carefully remove the existing wall mounted sockets with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 14 |  | 0
E | Carefully remove the existing wall mounted switches with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 18 |  | 0
F | Carefully remove the existing wall mounted cooker control unit with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 1 |  | 0
G | Carefully remove the existing ceiling mounted light fittings unit with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 65 |  | 0
H | Include provisional for careful removal of fire fighting equipment and installations by a specialist Contractor and set aside as directed by the Client | item | 1 |  | 0
J | Include provisional for additional demolition works and set aside as directed by the Client | item | 1 |  | 0
|  | TO COLLECTION ZMK |  |  | 0
COLLECTION
|  |  |  | Page 1 | 0
|  |  |  | Page 2 | 0
|  |  |  | Page 3 | 0
|  |  |  | Page 4 | 0
|  |  | TO SUMMARY ZMK |  | 0
Item | Description | Unit | Qty | Rate | Rate
Element 2 Refurbishment and New Works
CARPENTRY, JOINERY AND IRONMONGERY
Skirting in Laminate wrot softwood
A | Supply and fix 25 x 75mm Hardwood matching with doors, including jointing, angles and ends etc | m | 420 |  | 0
DOORS
Interior quality Hollow core flush doors covered on both sides with commercial venereed plywood laminated with edging strip all round
B | Supply and fix 44mm (finished) door size 725 x 1960mm maple/American Wallnut laminated flush doors in the toilets | No. | 9 |  | 0
C | Supply and fix 44mm (finished) door size 825 x 1960mm Hardwood modern interior doors complete with Door frame (To Clients approval) | No. | 9 |  | 0
Fire Glazed Door
D | Supply and fix 44mm (finished) fire door size 1325 x 1960mm and hung on butts hinges io existing metal frame | No. | 0 |  | 0
Kitchen Unit/Cabinets
E | Supply and fix 2,000 x 590 x 1000mm shaped standard medium density fibre board New Kitchen unit complete with sink and granite vanity top approved by the Client | Item | 1 |  | 0
| Supply and install standard medium density fibre board Cabinets, WHB sinks in the toilets aproved by the clients. complete with granite vanity top approved by the Client | Item | 3
Ironmongery
F | Supply and fix 2 lever union motice lock with chromium plated forend and set of chromium plated finished lever handle furniture part fixed to metal | No. | 12 |  | 0
Sundries
G | Supply and fix door stop | No. | 12 |  | 0
H | Supply and fix 'Union' aluminium door stop chrome finished catalogue no. AL8370CH | No. | 12 |  | 0
I | Supply and fix approved edge trim to the wall tiles in the Toilets | m | 140 |  | 0
|  | TO SUMMARY ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
ALUMINIUM WORKS
Doors and entrance screens in Black factory coated aluminium glazed with 6.38mm thick laminated clear glass fixed with lugs and raw bolts, wedged and silicon sealant to glazing on spacers and setting blocks including all ironmongery and build in as described
A | Supply and fix Approved aluminium section (fire glazed and zanaco branded) in double shopfront doors comprising 2 No. open able lights size 900 x 2000mm each with high natural anodised approved aluminium frame, glazing thickness 6.4mm laminated safety glass,with butt hinges, handles, lock, door type PD1 overall size 1800 x 2400mm, 400mm louvered on top | No | 3 |  | 0
B | Supply and fix Approved aluminium section (Zanaco branded) in single shopfront doors comprising 1 No. open able light size 900 x 2000mm each with high Black approved aluminium frame, glazing thickness 6.4mm laminated safety glass,with butt hinges, handles, lock, door type AD2 overall size 900 x 2400mm, 400mm louvered on top | No | 2 |  | 0
Partitioning in Black aluminium framing glazed with 6.38mm clear laminated safety glass (Doors and Entrance screens measured separately)
C | Supply and fix 2.8metres high in three rows and vertical frames not exceeding 1metre centres top row 600mm high in 4 no. 6.38mm frosted louvre blades laminated safety glass, and middle row 1,100mm and 1,100mm bottom row in 6.38mm frosted aluminium glazing together with aluminium framing in full height, Zanaco branded up to 1200mm height | m2 | 96 |  | 0
|  | TO SUMMARY ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
PLUMBING INSTALLATIONS
(ALL PROVISIONAL)
Waste Water pipe
UPVC tubing and fixing in accordance with the recommended manufacturers instructions and as shown on relevant drawings
A | Supply and fix 40mm diameter waste pipe fixed to wall | m | 30 |  | 0
0
B | Supply and fix 50mm diameter waste pipe fixed to wall | m | 30 |  | 0
0
| Extra over the foregoing pipe work for the following fittings |  |  |  | 0
0
C | 40mm plain bend | No. | 5 |  | 0
0
D | 40mm bend with inspection eye | No. | 5 |  | 0
0
E | 50mm plain bend | No. | 5 |  | 0
0
F | 50mm bend with inspection eye | No. | 5 |  | 0
0
G | 50 x 50 x 40mm reducing tee | No. | 3 |  | 0
0
| Brasswork and Sundries |  |  |  | 0
0
H | 32mm diameter rubber P trap complete with chromium plated finished grating and joints to fitting and PVC tubing | No. | 4 |  | 0
0
| Water Supply |  |  |  | 0
0
| Chlorinated PVC (cPVC) as 'GENOVA' or PPR ' LAMASAT' tubing and fixing in accordance with the recommended manufacturers instructions and as shown on relevant drawings |  |  |  | 0
0
I | Supply and fix 15mm diameter waste pipe fixed to wall | m | 40 |  | 0
0
| Extra over the foregoing pipe work for the following fittings |  |  |  | 0
0
J | 15mm plain bend | No. | 6.6667 |  | 0
0
K | 15mm tee | No. | 6 |  | 0
0
L | 19 x 19 x 15mm reducing tee | No. | 2 |  | 0
0
| Brasswork and Sundries |  |  |  | 0
0
M | 15mm diameter steel braided flexible connectore 300mm long bent as required including brass unions at both ends and jointing to stop cork valve and sanitary fitting | No. | 6 |  | 0
0
N | 15mm Brass stop cock 1/4 turn as 'Cobra' and joints to cpvc | No. | 6 |  | 0
0
| Sanitary Fittings |  |  |  | 0
0
O | Supply and fix master flush urinals complete with waste, and accessories fixed to walls | No | 3 |  | 0
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
A | Supply and fix White glazed vitreous china drop- in wash hand basin as Vaal Sola or other equal and approved complete with 1 Nr. 15 mm high neck pillar tap as Cobra 401, plastic plug, chromium plated chain and 32 mm waste supported on granite top, size 560 x 450 mm | No | 5 |  | 0
0
B | Supply and fix White glazed vitreous china W.C. suite as Vaal Aquasive or other equal and approved complete with wash down pan with P trap and domex screws, 9 litre vitreous china cistern with side supply and overflow, plastic syphon fittings and flush pipe, black heavy duty plastic seat and cover, fixing to wall and floor and connectiong to supply, overflow and drain pipes | No | 6 |  | 0
0
C | Supply and fix Stainless steel Single bowl single drainer sink complete with chromium plated mixer unit and brackets, 38 mm chromium plated waste, chain and plastic plug , mounted on concrete or timber worktop or fixed to wall with concealed steel brackets, overall size 600 x 1600 mm, complete with a vanity top | nr | 1 |  | 0
0
D | Supply and fix approved soap dispenser | No | 4 |  | 0
0
E | Supply and fix approved Hand drier | No | 2 |  | 0
0
F | Supply and fix toilet roll holder | nr | 5 |  | 0
0
| Fittings |  |  |  | 0
0
G | 6mm Polished float glass silvered mirror and fixing to wall with double sided tape and chrome plated dome screws. Size 1500 x 600mm, Complete with Led strip or Back illumination as directed by client | No | 3 |  | 0
0
H | Supply and fix 30mm thick granite top with polished and slightly chamfered edges with cut out for sink | m2 | 0 |  | 0
0
I | Supply and fix 30mm thick granite top with polished and slightly chamfered edges with cut outs for drop-in wash hand basins | m2 | 6 |  | 0
0
J | Supply and fix Chromium plated towel rail complete with end brackets fixed to wall, 800 mm long and 20 mm diameter in the toilet and kitchen | nr | 3 |  | 0
0
| Existing Service Duct (All Provisional) |  |  |  | 0
0
K | Allow for checking the existing service duct for any leakages and make good any damaged pipes | Item | 2 |  | 0
0
| Testing |  |  |  | 0
0
L | Include for testing the whole of the plumbing installations on completion or as sections are completed , by means of water pressure test to one and a half times the working pressure. The Contractor is to include for executing a running test on full completion of the installation as required by the Client and the correct operation of all components shall be ascertained and the system properly balanced and all controls, valves, etc set to the satisfaction of the Client including providing all necessary water, electric power etc required for testing | Item | 1 |  | 0
0
| Chlorination |  |  |  | 0
0
M | Include for sterilising the whole of the plumbing installations after testing in accordance with the method laid down in the British code of practice No. 310 clause 506, all to the satisfaction of the Client | Item | 1 |  | 0
|  | TO COLLECTION ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
COLLECTION ZMK
|  |  |  | Page 7 | 0
|  |  |  | Page 8 | 0
|  | TO SUMMARY ZMK |  |  | 0
|  | TO SUMMARY ZMK |  |  | #REF!
Item | Description | Unit | Qty | Rate | Amount K n
ELECTRICAL INSTALLATIONS
LIGHT FITTINGS
The following light fittings inclusive of lamp, starter, flexible cord and the like
A | Supply and fix 600 x 600mm,LED light fitting with warm white tube with metallic body, Approved by Client | No | 85 |  | 0
0
B | Supply and fix 4 x 36W, 600mm long recessed mounted batten fluorescent light fitting with cool white tube with metallic body, start gear as PHILIPS TBS 269 4 x 18 W ELB recessed fluorescent C/W LBR diffuser | No | 6 |  | 0
0
C | Supply and fix 2 x 18W, Compact fluorescent light fitting surface mounted, white metallic body with OPAL BAYONET lock on glass shade as RADIANT JL20 1 x 18W CFL | No | 6 |  | 0
0
D | Supply and fix 4 x 36W, 1200mm long recessed mounted batten fluorescent light fitting with cool white tube with metallic body, start gear as PHILIPS TBS 269 4 x 18 W ELB recessed fluorescent C/W LBR diffuser | No | 5 |  | 0
0
E | Supply and fix down lighters to clients' approval | No | 23 |  | 0
0
0
F | Supply and fix Two compartment PVC power/data trunking to Offices complete with power and data cables | m | 45 |  | 0
0
| Supply and install power poles complete with power and data accessories |  |  |  | 0
0
G | Supply, deliver and fix power solution units to Boardroom table tops complete with accessories including cabling | No. | 10 |  | 0
0
| Checking Existing Sockets |  |  |  | 0
0
H | Allow for checking 8No. None functioning double sockets | item | 1 |  | 0
0
| CABLE TRAY COMPLETE WITH ACCESSORIES |  |  |  | 0
0
| Supply and install the following cable trays, bends, tees complete with mounting brackets and all required accessories |  |  |  | 0
0
I | Supply 300mm wide, medium duty return flange cable tray in hot dip galvanised with 02No. Dividers for power, data and telephone cables in ceiling void | m | 45 |  | 0
0
| Supply and install the following sockets, switches complete with associated cabling |  |  |  | 0
0
J | Supply and fix double sockets | No. | 45 |  | 0
0
K | Supply and fix switches | No. | 20 |  | 0
0
L | Supply and fix cooker control unit | No. | 1 |  | 0
0
M | Supply and fix RJ45 wall jacks data points | No. | 35 |  | 0
|  | TO SUMMARY ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
N | Supply and install Cat 6e data cable or equavilent to Hamms or approved. | m | 1250 |  | 0
0
O | Supply and fix drop points complete with accessories | No. | 12 |  | 0
0
0
| FLOOR, WALL AND CEILING FINISHES |  |  |  | 0
0
A | Supply and fix heavy duty rubberised carpet tiles, Belgotex Berber point 920-Neutral Beige to manufacturers detail and specifications | m2 | 250 |  | 0
| Supply and fix heavy duty carpet tiles, Atlantis radiant rubberised per samples provided | m2 | 100
0
B | Supply and fix Ceramic floor tiles to manufacturers detail and specifications | m2 | 28 |  | 0
0
C | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails | m2 | 115 |  | 0
0
D | Supply and fix 300 x 600mm white glazed wall tiles with approved adhesive up to 2m high in the Toilets | m2 | 130 |  | 0
0
E | Supply and install sound proof barrier between office and Soft Lounge | item | 1 |  | 0
0
F | Expose and rectify leaks in the walls | item | 1 |  | 0
0
G | Supply and fix 300 x 600mm white/Grey glazed wall tiles with approved adhesive up to 600mm high in the Kitchen | m2 | 2 |  | 0
0
H | Supply and fix 600 x 600mm white/grey ceramic floor tiles with approved tile fix/adhesive in the Kitchen | m2 | 7 |  | 0
0
| CEILINGS |  |  |  | 0
0
| 600 x 600mm suspened mineral fibre acoustic ceiling tiles laid perfectly level on and including aluminium suspended T38 metal grid system |  |  |  | 0
0
I | Supply and fix 600 x 600mm Acoustic ceiling board including Dorn QRC 137K ceiling grid to specialist detail and specifications | m2 | 385 |  | 0
|  | TO SUMMARY ZMK |  |  | 0
Item | Description | Unit | Qty | Rate | Amount K n
PAINTING AND DECORATING
Prepare and apply one undercoat and three coats PVA ZANACO warm white paint on the following surfaces as described
A | Supply and paint plastered walls in one undercoat and two coats Luxurious Silk, Zanaco approved paint | m2 | 130 |  | 0
0
B | Supply and paint plastered walls in one undercoat and two coats zanaco warm white paint on landing and stairs has directed. | m2 | 50 |  | 0
0
| Knot, prime, stop and apply one undercoat and two high glossenamel Zanaco beige to the following surfaces |  |  |  | 0
0
C | To existing door frames | m2 | 20 |  | 0
D | Apply two coats textured paint to surfaces of column,walls and dry walls | m2 | 30 |  | 0
0
TO COLLECTION ZMK
Item | Description | Unit | Qty | Rate | Amount K n
PROVISIONAL SUMS
A |  |  |  |  | 0
| Include provisional for Inetrior Design Services | item | 1 | 200000 | 200000
B |  |  |  |  | 0
| Include for provisional for additional electrical installations | item | 1 | 5000 | 5000
0
| FIRE ALARM SYSTEM |  |  |  | 0
C |  |  |  |  | 0
| Include provisional for Supply and fix of fire fighting equipment and Alarm system installations by a specialist Contractor (Premium fire) or any other approved by the CLIENT, including main contractor mark up and attendance | item | 1 | 25000 | 25000
0
| Include provisional for fire exit signs and drawings | item | 1 | 5000 | 5000
D |  |  |  |  | 0
| SECURITY AND CCTV INSTALLATION |  |  |  | 0
0
| Include provisional for supply and fix security equipment and CCTV installations by a specialist Contractor, (DCS) or any other approved by the Client, including main contractor mark up and attendance | item | 1 | 17500 | 17500
E |  |  |  |  | 0
| BRANDING |  |  |  | 0
0
| Include provisional for branding Specialist approved by the Client, including main contractor mark up and attendance | item | 1 | 20000 | 20000
0
F | IT Works |  |  |  | 0
| Include for provisional for additional IT installations | item | 1 | 15000 | 15000
|  | TO SUMMARY ZMK |  |  | 287500
Item
| Description | Unit | Qty | Rate | Amount K n
SUMMARY
A |  |  |  |  | 0
DEMOLITION WORKS
B |  |  |  |  | 0
CARPENTRY, JOINERY AND IRONMONGERY
C |  |  |  |  | 0
ALUMINIUM WORKS
D |  |  |  |  | 0
PLUMBING INSTALLATIONS
F |  |  |  |  | 0
ELECTRICAL INSTALLATIONS
G |  |  |  |  | 0
FLOOR, WALL AND CEILING FINISHES
H
PAINTING AND DECORATING
I
PROVISIONAL SUMS
| Subtotal 1 | K
Contigency 10%
Subtotal 2
VAT 16%
| Total Sum to Form of Tender | K
0