## VALUATION (hidden)
HONG CHEN CONSTRUCTION LIMITED
CLAIM NO. 03
| PROJECT MANAGER: ZANACO |  | CONTRACT: PROPOSED REFURBISHMENT WORKS
AT ZANACO HEAD OFFICE 8TH FLOOR
| CONTRACTOR: HONG CHEN CONSTRUCTION LTD |  | CONTRACT SUM (VAT INCLUSIVE) |  | 3300638.1
PLOT NO. 225 MAPOSA ROAD, CHAMBA VALLEY,
LUSAKA - ZAMBIA
DATE OF CLAIM: 17/11/2020
| VALUATION FOR FINAL ACCOUNT CERTIFICATE NO. | 3
|  | A CONTRACT SUM | B CURRENT CONTRACT VALUE | C CURRENT VALUATION | D CURRENT AMOUNT CERTIFIED
1 | Value of Work Executed |  |  | #REF!
2 | Materials on Site |  |  | 0
3 | Materials off Site
4 | Less: Retention @ 5% |  |  | #REF!
5 | Add: Advance Payment
6 | Net Contract Sum (without VAT) | #REF!
7 | Authorised Adjustments
8 | Contract Price Adjustment | #REF! |  | #REF! | #REF!
9 | GROSS AMOUNT AMOUNT CERTIFIED |  |  |  | #REF!
10 | Less: Liquidated damages | 100% |  |  | 28000
11 | Less: Previous Amount Certified before VAT |  |  |  | 1862744.46
| NET AMOUNT CERTIFIED |  |  |  | #REF!
12 | Less: Contract Claims |  |  |  | 0
| SUB-TOTAL | #REF! |  |  | #REF!
13 | Add: VAT @ 16% | #REF! |  |  | #REF!
| TOTAL | #REF! |  |  | #REF!
14 | AMOUNT NOW DUE TO THE CONTRACTOR IN THIS VALUATION (ZMK) |  |  |  | #REF!
The above net valuation is issued, without prejudice to its amendments, in accordance with the conditions of contract and is
subject to all materials and workmanship to which it relates being approved.
| COPY: Project Manager |  | …………………………………………………………
Contractor
Employer

## 9th Floor
Item | Description | Unit | Qty | Re-Measure | Accummulative Qty | Rate | Rate | Accummulative Amount K n |  | Accummulative Amount K n | Amount (ZMW)
| Proposed Refurbishment Works to the 9th Floor, Zambia National Commercial Bank Headquarters, Cairo Road, Lusaka. | [8 empty] | 0
| Bill Nr 2 : 9th Floor Refurbishment Works | [8 empty] | 0
| Element 1 Demolition Works | [8 empty] | 0
0
| NATURE OF THE WORK | [8 empty] | 0
0
| The bidder is advised to conduct a site visit before pricing this document | [8 empty] | 0
A | The bidder is advised to visit the site and satisfy himself as to the extent and nature of the works. The Contractor must conform to the instructions of the Client in carrying out any portion of the work which in his opinion requires to be expedited and the Contractor shall give priority to such work as and when directed | [8 empty] | 0
0
| SAFETY | [8 empty] | 0
0
B | High safety standards shall be observed for the whole duration of the works | [7 empty] | Z171PB/S005/1-36A | 0
0
| ELECTRIC WIRES, PIPES, ETC | [8 empty] | 0
0
C | Special care is to be taken not to interfere unnecessarily with any electric light, power or telephone wires and fittings that may be met with and notice is to be given to the Client when any disconnections or removal of wires etc are necessary, and the contractor is to afford every facility to the person carrying out this work. | [8 empty] | 0
0
D | Any water supply, waste or other piping that may be met with and found necessary to disconnect or cut are to be effectively stopped off and any new connections that may be necessary are to be made with proper fittings and to the satisfaction of the Client to whom due notice must be given of any alterations to the existing services | [8 empty] | 0
0
| PROTECTION | [8 empty] | 0
0
E | In taking down and removing existing work utmost care is to be taken to avoid any structural or other damage to the remaining portions of the building, and the work is to be carried out in a workmanlike, practical and safe manner, under the constant supervision of a competent foreman. The Contractor must also protect all work not removed such as walls, floors, doors, windows, or other joinery, loose and fixed fittings and electrical appliances etc. from damage during the progress of the work and provide all necessary materials for doing so. The Contractor will be held responsible for any damage to persons or property and for the safety of the structure throughout the whole of this contract and must be made good at his own expense any damage that may occur. | [8 empty] | 0
0
| MATERIALS FROM DEMOLITIONS | [8 empty] | 0
0
F | All the materials from demolitions are to become the property of the Client, except where stated otherwise, and can only be removed from site and CREDIT is to be allowed for the same under the work section stated once the Client advises so | [8 empty] | 0
0
G | Any sound material which is in good condition may, with the Client's written consent, be re-used. Old materials specified to be set aside for re-use are to be carefully removed, cleaned, stored, protected and made good as required | [8 empty] | 0
0
|  | TO COLLECTION ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
DISTURBANCE, DUST AND NOISE PROTECTION
A | The Bank will continue to operate throughout the construction works Contract and the Contractor will be required to carry out the work in the most careful manner so as to minimise noise, inconvinience and disturbance to the public and all neighbourhood. The Contractor is to supply , install or erect all equipment and materials necessary for the complete dust protection of all areas in operation during the execution of work in such areas to the satisfaction of the Client and remove when directed
NOTICES
B | Give all notices to the Municipality and/or Authorities and pay charges legally payable and include for the removal or alteration or disconnection of electric wires or cables, telephone wires, etc, which may be met
DEMOLITION WORKS
Lay-in Ceiling
C | Carefully remove the existing ceiling panels together with associated works, light fittings, make good works disturbed, clear away from site and prepare to receive new ceiling works | m2 | 430 | 430 | 430
Partition
D | Demolish glazed aluminium partion approximately 4.5 x 2.8m high, make good works disturbed and clear away debris from site as directed by Client ( ELEVATOR LOBBY) | Item | 1 | 1 | 1
E | Carefully remove the existing drywall timber partition walls together with associated works, make good works disturbed, clear away debris from site and prepare to receive new aluminium partitions | m2 | 330 | 330 | 330
F | Carefully sand down and prepare drywall partition walls to receive new zanaco warm white paint | m2 | 120 | 120 | 120
Sanitary fittings
G | Carefully remove the existing disfunctional geyser with associated pipes and accessories and prepare surface to make good in the kitchen and store as directed by client | item | 1 | 1 | 1
H | Carefully remove the existing disfunctional geyser with associated pipes and accessories and prepare surface to make good in the toilets and store as directed by client | item | 1 | 0 | 1
I | Carefully remove the existing watercloset together with cistern with associated pipes and accessories and prepare surface to receive new water closets and store as directed by client | item | 3 | 3 | 3
J | Carefully remove the existing wash hand basins with associated pipes and accessories and prepare surface to receive new wash hand basins and store as directed by client | item | 4 | 4 | 4
K | Carefully remove the existing hand driers with associated accessories and prepare surface to receive new hand driers and store as directed by client | item | 2 | 0 | 2
|  | TO COLLECTION ZMW | [5 empty] | 0 |  | 0
0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  | #VALUE! | Amount (ZMW)
A | Carefully remove the existing soap dispensers with associated accessories and prepare surface to receive new soap dispensers and store as directed by client | item | 4 | 2 | 2
B | Carefully remove the existing toilet roll holders with associated accessories and prepare surface to receive new toilet roll holders and store as directed by client | item | 3 | 0 | 3
C | Carefully remove the existing urinals with associated pipes and accessories and prepare surface to receive new urinals and store as directed by client | item | 3 | 3 | 3
D | Carefully remove the existing kitchen sink with associated pipes and accessories and prepare surface to receive new drop in sink and store as directed by client | item | 1 | 1 | 1
Floor, Wall tiling and finishes
E | Carefully remove the existing PVC floor tiles together with associated works, make good all works disturbed and prepare to receive new Belgotex carpet tiles -Berber point 920 - heavy duty Neutral berge and store as directed by Client | m2 | 430 | 430 | 430
F | Carefully remove the existing PVC floor tiles together with associated works, make good all work disturbed and prepare to receive new ceramic tiles in the kitchen and store as directed by the Client | m2 | 7 | 7 | 7
G | Carefully remove the existing white glazed wall tiles together with associated works, make good all works disturbed and prepare to receive new wall tiles in the Toilets, store as directed by the Client | m2 | 130 | 130 | 130
H | Carefully sand down and prepare plastered walls to receive new zanaco warm white paint | m2 | 130 | 130 | 130
Doors
I | Carefully remove existing 725 x 1960mm doors and prepare receive new doors to the toilets and store as directed by client | No | 9 | 1 | 9
J | Carefully remove the existing 825 x 1960mm door and prepare receive new door to the kitchen and store as directed by client | No | 1 | 1 | 1
K | Carefully remove the existing 825 x 1960mm door together with frames mounted on partition walls in offices and prepare to receive new doors and store as directed by client | Item | 11 | 8 | 8
L | Carefully remove the existing double door together with frames mounted on partition walls in conference Room and prepare to receive new doors and store as directed by client | Item | 1 | 0 | 1
M | Carefully remove the existing double aluminium door together with frames mounted on partition walls at the Entrance from the Foyer and prepare to receive new doors and store as directed by client | Item | 3 | 2 | 2
Air-conditioning Installations
N | Carefully remove the existing wall mounted airconditioners with associated external units and accessories and prepare surface to make good and keep for reuse as directed by client | item | 5 | 3 | 5
|  | TO COLLECTION ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
A | Carefully remove the existing ceiling mounted airconditioners with associated external units and accessories and prepare surface to make good and keep for reuse as directed by client | item | 6 | 3 | 6
Electrical Installations
B | Carefully remove the existing metal trunking together with associated works, data and electrical cables, data points and sockets and prepare to receive new trunking | m | 50 | 50 | 50
C | Carefully remove the existing wall mounted data points with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 20 | 20 | 20
D | Carefully remove the existing wall mounted sockets with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 14 | 17 | 14
E | Carefully remove the existing wall mounted switches with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 18 | 18 | 18
F | Carefully remove the existing wall mounted cooker control unit with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 1 | 1 | 1
G | Carefully remove the existing ceiling mounted light fittings unit with associated cables and accessories and prepare surface to receive new ones and store as directed by client | No. | 85 | 65 | 65
H | Include provisional for careful removal of fire fighting equipment and installations by a specialist Contractor and set aside as directed by the Client | item | 1 | 1 | 1
I | Include provisional for careful removal of security equipment and CCTV installations by a specialist Contractor and set aside as directed by the Client | item | 1 | 1 | 1
J | Include provisional for additional demolition works and set aside as directed by the Client | item | 1 | 0 | 1
|  | TO COLLECTION ZMW | [5 empty] | 0 |  | 0
COLLECTION
[6 empty] | Page 1 | Page 1 | 0
[6 empty] | Page 2 | Page 2 | 0 |  | 0 | 0
[6 empty] | Page 3 | Page 3 | 0 |  | 0 | 0
[6 empty] | Page 4 | Page 4 | 0 |  | 0 | 0
|  |  | TO SUMMARY ZMK |  |  |  |  | 0 |  | 0 | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
Element 2 Refurbishment and New Works
CARPENTRY, JOINERY AND IRONMONGERY
Skirting in Laminate wrot softwood
A | Supply and fix 25 x 75mm laminate skirting including jointing, angles and ends etc | m | 420 | 420 | 420
DOORS
Interior quality Hollow core flush doors covered on both sides with commercial venereed plywood laminated with edging strip all round
B | Supply and fix 44mm (finished) door size 725 x 1960mm maple laminated flush doors in the toilets | No. | 9 | 1 | 1
C | Supply and fix 44mm (finished) door size 825 x 1960mm maple laminated flush doors | No. | 3 | 3 | 3
Fire Glazed Door
D | Supply and fix 44mm (finished) fire door size 1325 x 1960mm and hung on butts hinges io existing metal frame | No. | 0 |  | 0
Kitchen Unit
E | Supply and fix 2,000 x 590 x 1000mm shaped standard medium density fibre board New Kitchen unit complete with sink and granite vanity top approved by the Client | Item | 1 | 1 | 1
Ironmongery
F | Supply and fix 2 lever union motice lock with chromium plated forend and set of chromium plated finished lever handle furniture part fixed to metal | No. | 12 | 12 | 12
Sundries
G | Supply and fix door stop | No. | 12 | 6 | 6
H | Supply and fix 'Union' aluminium door stop chrome finished catalogue no. AL8370CH | No. | 18 | 0 | 0
I | Supply and fix approved edge trim to the wall tiles in the Toilets | m | 140 | 120 | 120
|  | TO SUMMARY ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
ALUMINIUM WORKS
Doors and entrance screens in black mat finish aluminium glazed with 6.38mm thick laminated clear glass fixed with lugs and raw bolts, wedged and silicon sealant to glazing on spacers and setting blocks including all ironmongery and build in as described
A | Supply and fix Approved black mat finish aluminium section (fire glazed and zanaco branded) in double shopfront doors comprising 2 No. open able lights size 900 x 2000mm each with black mat finish approved aluminium frame, glazing thickness 6.4mm laminated safety glass,with butt hinges, handles, lock, door type PD1 overall size 1800 x 2400mm, 400mm casement openable on top | No | 2 | 0 | 0
B | Supply and fix Approved aluminium section (Zanaco branded) in single shopfront doors comprising 1 No. open able light size 900 x 2000mm each with high natural anodised approved aluminium frame, glazing thickness 6.4mm laminated safety glass,with butt hinges, handles, lock, door type AD2 overall size 900 x 2400mm, 400mm louvered on top | No | 4 | 0 | 0
Partitioning in black mat finish aluminium framing glazed with 6.38mm clear laminated safety glass (Doors and Entrance screens measured separately)
C | Supply and fix 2.8metres high in three rows and vertical frames not exceeding 1metre centres top row 600mm high in 4 no. 6.38mm frosted louvre blades laminated safety glass, and middle row 1,100mm and 1,100mm bottom row in 6.38mm frosted aluminium glazing together with aluminium framing in full height, Zanaco branded up to 1200mm height | m2 | 96 | 0 | 0
|  | TO SUMMARY ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
PLUMBING INSTALLATIONS
(ALL PROVISIONAL)
Waste Water pipe
UPVC tubing and fixing in accordance with the recommended manufacturers instructions and as shown on relevant drawings
A | Supply and fix 40mm diameter waste pipe fixed to wall | m | 30 | 5 | 5
B | Supply and fix 50mm diameter waste pipe fixed to wall | m | 30 | 5 | 5
Extra over the foregoing pipe work for the following fittings
C | 40mm plain bend | No. | 5 | 5 | 5
D | 40mm bend with inspection eye | No. | 5 | 5 | 5
E | 50mm plain bend | No. | 5 | 5 | 5
F | 50mm bend with inspection eye | No. | 5 | 5 | 5
G | 50 x 50 x 40mm reducing tee | No. | 3 | 3 | 3
Brasswork and Sundries
H | 32mm diameter rubber P trap complete with chromium plated finished grating and joints to fitting and PVC tubing | No. | 4 | 2 | 2
Water Supply
Chlorinated PVC (cPVC) as 'GENOVA' or PPR ' LAMASAT' tubing and fixing in accordance with the recommended manufacturers instructions and as shown on relevant drawings
I | Supply and fix 15mm diameter waste pipe fixed to wall | m | 40 | 20 | 20
Extra over the foregoing pipe work for the following fittings
J | 15mm plain bend | No. | 6.6667 | 5 | 5
K | 15mm tee | No. | 4 | 2 | 2
L | 19 x 19 x 15mm reducing tee | No. | 2 | 1 | 1
Brasswork and Sundries
M | 15mm diameter steel braided flexible connectore 300mm long bent as required including brass unions at both ends and jointing to stop cork valve and sanitary fitting | No. | 4 | 2 | 2
N | 15mm Brass stop cock 1/4 turn as 'Cobra' and joints to cpvc | No. | 4 | 2 | 2
Sanitary Fittings
O | Supply and fix master flush urinals complete with waste, and accessories fixed to walls | No | 3 | 3 | 3
|  | TO COLLECTION ZMKW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
A | Supply and fix White glazed vitreous china drop- in wash hand basin as Vaal Sola or other equal and approved complete with 1 Nr. 15 mm high neck pillar tap as Cobra 401, plastic plug, chromium plated chain and 32 mm waste supported on granite top, size 560 x 450 mm | No | 4 | 0 | 4
B | Supply and fix White glazed vitreous china W.C. suite as Vaal Aquasive or other equal and approved complete with wash down pan with P trap and domex screws, 9 litre vitreous china cistern with side supply and overflow, plastic syphon fittings and flush pipe, black heavy duty plastic seat and cover, fixing to wall and floor and connectiong to supply, overflow and drain pipes | No | 5 | 4 | 4
C | Supply and fix Stainless steel Single bowl single drainer sink complete with chromium plated mixer unit and brackets, 38 mm chromium plated waste, chain and plastic plug , mounted on concrete or timber worktop or fixed to wall with concealed steel brackets, overall size 600 x 1600 mm, complete with a vanity top | nr | 2 | 1 | 2
D | Supply and fix approved soap dispenser | No | 4 | 4 | 4
E | Supply and fix approved Hand drier | No | 2 | 2 | 2
F | Supply and fix toilet roll holder | nr | 5 | 0 | 4
Fittings
G | 6mm Polished float glass silvered mirror and fixing to wall with double sided tape and chrome plated dome screws. Size 1500 x 600mm | No | 2 | 0 | 0
H | Supply and fix 30mm thick granite top with polished and slightly chamfered edges with cut out for sink | m2 | 4 | 0 | 0
I | Supply and fix 30mm thick granite top with polished and slightly chamfered edges with cut outs for drop-in wash hand basins | m2 | 6 | 3 | 3
J | Supply and fix Chromium plated towel rail complete with end brackets fixed to wall, 800 mm long and 20 mm diameter in the toilet and kitchen | nr | 3 |  | 3
Existing Service Duct (All Provisional)
K | Allow for checking the existing service duct for any leakages and make good any damaged pipes | Item | 2 | 0 | 2
Testing
L | Include for testing the whole of the plumbing installations on completion or as sections are completed , by means of water pressure test to one and a half times the working pressure. The Contractor is to include for executing a running test on full completion of the installation as required by the Client and the correct operation of all components shall be ascertained and the system properly balanced and all controls, valves, etc set to the satisfaction of the Client including providing all necessary water, electric power etc required for testing | Item | 1 | 0 | 1
Chlorination
M | Include for sterilising the whole of the plumbing installations after testing in accordance with the method laid down in the British code of practice No. 310 clause 506, all to the satisfaction of the Client | Item | 1
|  | TO COLLECTION ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
COLLECTION ZMK
[6 empty] | Page 7 | Page 7 | 0 |  | 0 | 0
[6 empty] | Page 8 | Page 8 | 0 |  | 0 | 0
|  | TO SUMMARY ZMW | [5 empty] | 0 |  | 0 | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
AIR-CONDITIONING AND VENTILATION INSTALLATIONS
(ALL PROVISIONAL)
Preambles
The system as designed is for LG Equipment. However, the Tenderer is allowed to price for other equal and approved equipment from other reputable suppliers
Supply, install, test, comissioning and handover the following Airconditioning and Ventilation systems
In-door Units
A | LG' Ceiling concealed ducted Split Air Conditioning Unit as TB-H186HSS1 or other equal and approved
Cooling Capacity - 24,000Btu/Hr
Heating Capacity - 24,000 Btu/Hr
Electrics - 240V/1PH/50HZ 1.9KV
| complete with remote control and all ancillary fittings | No. | 0
B | LG' Ceiling concealed ducted Split Air Conditioning Unit as LT- (C)H286HLE or other equal and approved
Cooling Capacity - 28,000Btu/Hr
Heating Capacity - 30,000 Btu/Hr
Electrics - 360V/1PH/50HZ 2.9KV
| complete with remote control and all ancillary fittings | No. | 0
Mid-wall Units
C | LG' mid - wall Split Air Conditioning Unit as KS - H186CU1 or other equal and approved
Cooling Capacity - 18,500Btu/Hr
Heating Capacity - 19,500 Btu/Hr
Electrics - 240V/1PH/50HZ 2.9KV
| complete with remote control and all ancillary fittings | No. | 0
D | LG' mid - wall Split Air Conditioning Unit as KS - H186CU1 or other equal and approved
Cooling Capacity - 18,500Btu/Hr
Heating Capacity - 19,500 Btu/Hr
Electrics - 240V/1PH/50HZ 2.9KV
| complete with remote control and all ancillary fittings | No. | 0
Duct work
Flexible duct as 'EUROPAIR' thermal insulated sodec type 25P Euroflex flexible ducting and fixing in accordance with the manufacturers instructions complete with all necessary supports, fittings, brackets and fixings
E | Supply and fix 150mm diameter flexible duct | m | 0
|  | TO COLLECTION ZMKW | [5 empty] | 0 |  | 0 | Omit
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
A | Supply and fix 200mm diameter flexible duct | m | 0
B | Supply and fix 250mm diameter flexible duct | m | 0
C | Extra over flexible duct for 150mm bend | No. | 0
D | Ditto for 200mm bend | No. | 0
E | Ditto for 150 x 200 x 200mm tee | No. | 0
Refridgerant gas/Liquid pipes and condensate drain pipes
COPPER TUBING as described complete with all fittings and armaflex insulations and fixing in accordance with the manufacturers instructions complete with all necessary supports, fittings, brackets and fixings
F | Allow for all liquid refridgerant copper tubing | Iitem | 0
G | Allow for all gas refridgerant copper tubing | Iitem | 0
PVC CONDENSATE DRAIN PIPES AND FITTINGS and fixing in accordance with the manufacturers instructions complete with necessary support brackets and insulation as shown on drawings
H | Allow for all drain pipes | Iitem | 0
Cabling
I | 20mm diameter pvc conduit pipes in chases | m | 0
Re-use of Airconditioning Units
J | Take from store and fix wall mounted airconditioners together with external unit and accessories to clients' approved locations | No | 0
K | Take from store and fix ceiling mounted airconditioners together with external unit and accessories to clients' approved locations | No | 0
|  | TO COLLECTION ZMK | [5 empty] | 0 |  | 0 | Omit
COLLECTION
[6 empty] | Page 10 | Page 10 | 0 |  | 0 | Omit
[6 empty] | Page 11 | Page 11 | 0 |  | 0 | Omit
|  | TO SUMMARY ZMW | [5 empty] | 0 |  |  | Omit
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
ELECTRICAL INSTALLATIONS
LIGHT FITTINGS
The following light fittings inclusive of lamp, starter, flexible cord and the like
A | Supply and fix 4 x 36W, 600mm long recessed mounted LED fluorescent light fitting with warm white tube with metallic body, start gear as PHILIPS TBS 269 4 x 18 W ELB recessed fluorescent C/W LBR diffuser | No | 105 | 50 | 85
B | Supply and fix 4 x 36W, 600mm long recessed mounted LED fluorescent light fitting with warm tube with metallic body, start gear as PHILIPS TBS 269 4 x 18 W ELB recessed fluorescent C/W LBR diffuser | No | 6 |  | 0
C | Supply and fix 2 x 18W, Compact fluorescent light fitting surface mounted, white metallic body with OPAL BAYONET lock on glass shade as RADIANT JL20 1 x 18W CFL | No | 6 |  | 0
D | Supply and fix 4 x 36W, 1200mm long recessed mounted LED fluorescent light fitting with warm white tube with metallic body, start gear as PHILIPS TBS 269 4 x 18 W ELB recessed fluorescent C/W LBR diffuser | No | 5 |  | 0
E | Supply and fix down lighters to clients' approval | No | 10 |  | 4
F | Supply and fix Two compartment PVC power/data trunking to Offices complete with power and data cables | m | 90 | 55 | 55
Supply and install power poles complete with power and data accessories
[8 empty] | 0 |  | 0 | 0
G | Supply, deliver and fix power poles complete with accessories including cabling | No. | 10 | 0 | 5
Checking Existing Sockets
H | Allow for checking 8No. None functioning double sockets | item | 1 | 1 | 1
CABLE TRAY COMPLETE WITH ACCESSORIES
Supply and install the following cable trays, bends, tees complete with mounting brackets and all required accessories
I | Supply 300mm wide, medium duty return flange cable tray in hot dip galvanised with 02No. Dividers for power, data and telephone cables in ceiling void | m | 80 | 60 | 78
[8 empty] | 0 |  | 0 | 0
| Supply and install the following sockets, switches complete with associated cabling | [6 empty] | 0 |  | 0 | 0
J | Supply and fix double sockets | No. | 45 | 35 | 35
K | Supply and fix switches | No. | 20 | 15 | 15
L | Supply and fix cooker control unit | No. | 1 | 0 | 1
M | Supply and fix RJ45 wall jacks data points | No. | 45 | 0 | 45
|  | TO SUMMARY ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  |  | Amount (ZMW)
N | Supply and install Cat 6e data cable or equavilent to Hamms or approved. | m | 1250 | 0 | 1250
O | Supply and fix drop points complete with accessories | No. | 12 | 5 | 5
FLOOR, WALL AND CEILING FINISHES
A | Supply and fix heavy duty carpet tiles, Belgotex Berber point 920-Neutral Beige to manufacturers detail and specifications | m2 | 350 | 0 | 350
B | Supply and fix Ceramic floor tiles to manufacturers detail and specifications | m2 | 28 | 28 | 28
C | Supply and fix vertical blinds in approved Ivory shade overall, complete with rails | m2 | 190 | 0 | 190
D | Supply and fix 300 x 600mm white glazed wall tiles with approved adhesive up to 2m high in the Toilets | m2 | 130 | 120 | 120
E | Supply and install sound proof barrier between office and Soft Lounge | item | 1 | 0 | 1
F | Expose and rectify leaks in the walls | item | 1 | 0 | 1
G | Supply and fix 300 x 600mm white glazed wall tiles with approved adhesive up to 600mm high in the Kitchen | m2 | 2 | 2 | 2
H | Supply and fix 600 x 600mm white ceramic floor tiles with approved tile fix/adhesive in the Kitchen | m2 | 7 | 5 | 6.5
CEILINGS
600 x 600mm suspened mineral fibre acoustic ceiling tiles laid perfectly level on and including aluminium suspended T38 metal grid system
I | Supply and fix 600 x 600mm Acoustic ceiling board including Dorn QRC 137K ceiling grid to specialist detail and specifications | m2 | 385
|  |  |  | 385 | 0
J | Supply and fix 600 x 600mm Acoustic ceiling board including Dorn QRC 137K ceiling grid to specialist detail and specifications for the landing | m2 | 45
|  | TO SUMMARY ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  | Amount K n | Amount (ZMW)
PAINTING AND DECORATING
Prepare and apply one undercoat and three coats PVA ZANACO warm white paint on the following surfaces as described
A | Supply and paint plastered walls in one undercoat and two coats zanaco warm white paint | m2 | 130 | 130 | 130
B | Supply and paint plastered walls in one undercoat and two coats zanaco warm white paint on landing and stairs has directed. | m2 | 50 | 50 | 50
Knot, prime, stop and apply one undercoat and two high glossenamel Zanaco beige to the following surfaces
C | To existing door frames | m2 | 20 | 20 | 20
Prepare, sand and apply one undercoat and three coats PVA ZANACO warm white paint on the following surfaces as described
D | existing timber partitioning internally | m2 | 120 | 120 | 120
|  | TO COLLECTION ZMW | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n |  | Amount K n | Amount (ZMW)
PROVISIONAL SUMS
A | Include provisional for vertical blinds | item | 1 | [7 empty] | 80000
B | Include for provisional for additional electrical installations | item | 1 | [7 empty] | 20000
FIRE ALARM SYSTEM
C | Include provisional for Supply and fix of fire fighting equipment and Alarm system installations by a specialist Contractor (Premium fire) approved by the CLIENT, including main contractor mark up and attendance | item | 1 | 0% | [6 empty] | 30000
| Include provisional for fire exit signs and drawings | item | 1 | [7 empty] | 5000
D | SECURITY AND CCTV INSTALLATION
| Include provisional for supply and fix security equipment and CCTV installations by a specialist Contractor, (DCS) approved by the Client, including main contractor mark up and attendance | item | 1 | [7 empty] | 10000
E | BRANDING
| Include provisional for branding Specialist approved by the Client, including main contractor mark up and attendance | item | 1 | [7 empty] | 10000
F | IT Works
| Include for provisional for additional IT installations | item | 1 | [7 empty] | 40000
[10 empty] | 0 | 0
|  | TO SUMMARY ZMK | [5 empty] | 0 |  | 0
Item | Description | Unit | Qty |  |  | Rate | Rate | Amount K n
| SUMMARY | [6 empty] | SUMMARY
A | DEMOLITION WORKS | [6 empty] | 0 |  | 0 | 0
B | CARPENTRY, JOINERY AND IRONMONGERY | [6 empty] | 0 |  | 0 | 0
C | ALUMINIUM WORKS | [6 empty] | 0 |  | 0 | 0
D | PLUMBING INSTALLATIONS | [6 empty] | 0 |  | 0 | 0
E | AIR-CONDITIONING AND VENTILATION INSTALLATIONS | [6 empty] | 0 |  | 0 | Omit
F | ELECTRICAL INSTALLATIONS | [6 empty] | 0 |  | 0 | 0
G | FLOOR, WALL AND CEILING FINISHES | [6 empty] | 0 |  | 0 | 0
H | PAINTING AND DECORATING | [6 empty] | 0 |  | 0 | 0
I | PROVISIONAL SUMS | [6 empty] | 0 |  | 0 | 0
| Subtotal 1 |  |  | K
Contigency 10%
Subtotal 2
VAT 16%
| 9th Floor BILL - TOTAL CARRIED TO FORM OF TENDER |  |  | K
| TO MAIN SUMMARY K | [6 empty] | 0 |  | 0